## Preschool Education AP
Sectoral priority 1 |  | Quality and sustainable education and science systems focused on the needs of students, society, and the state
Goal 1.1: |  |  | Ensuring a high-quality, supportive and development-oriented educational process by all early childhood and preschool care and education institutions |  |  |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  | Goal 4 Quality education Goal 8 Decent work and economic growth
Impact indicator 1.1.1: |  |  | Percentage share of authorized early and preschool care and education institutions in the total number. |  |  |  |  | Baseline | Goal |  |  | Source of verification
[9 empty] | Interim | Final
[7 empty] | Year | 2021 | 2025 | 2030 |  | Data from the National Center for Quality Enhancement
[7 empty] | Indicator | N/A | >10% | 100%
Objective 1.1.1: |  |  | Ensuring continuous professional development of preschool educators in each institution of early and preschool care and education
Outcome indicator 1.1.1.1: |  |  | The percentage share of preschool educators with a bachelor's degree in the total number |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Interim | Final
[7 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[7 empty] | Indicator | 35% | >50 % | > 60% | > 70%
Risk |  |  | Lack of human and financial resources
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
1.1.1.1 | Introduction of undergraduate programs of preschool education |  |  | 1.1.1.1(1) | Minimum 5 undergraduate programs are introduced | HEI's websites | HEIs | Ministry of Education and Science | III quarter of 2023 | Administrative cost
1.1.1.2 | Development of guiding principles and requirements for continuous professional development of educators-pedagogues |  |  | 1.1.1.2(1) | A policy document is developed at the central and local levels | Annual Report of the Ministry of Education and Science | TPDC/Ministry of Education and Science |  | IV quarter of 2022 | Administrative cost
1.1.1.3 | Evaluation of existing continuous professional development programs and providers, and development of recommendations regarding the design of continuous professional development programs framework |  |  | 1.1.1.3(1) | An analysis and recommendations for the development of a new methodology have been prepared | Annual Report of the Ministry of Education and Science | TPDC/Ministry of Education and Science |  | IV quarter of 2022 | 9600 | 9600 | 32 02 02
1.1.1.4 | Creation of a national database for the registration of educators-pedagogues |  |  | 1.1.1.4(1) | The databasee is created | EMIS database | EMIS/Ministry of Education and Science | Municipalities; TPDC | IV quarter of 2023 | 100000 |  |  | 100000 | UNICEF
1.1.1.5 | Creating a mandatory training module for continuous professional development on the holistic development pedagogy |  |  | 1.1.1.5(1) | Training module is created | Annual Report of the TPDC | TPDC/Ministry of Education and Science |  | II quarter, 2023 | Administrative cost
1.1.1.6 | Training of educators-pedagogues with holistic development pedagogy training module |  |  | 1.1.1.6(1) | Over 50% of educator-pedagogues are trained | EMIS database | TPDC/Ministry of Education and Science | Municipalities | IV quarter of 2024 | 13200 | 13200 | 32 02 02
1.1.1.7 | Development of differentiated training modules in the direction of inclusion for administration representatives and educators-pedagogues and their retraining |  |  | 1.1.1.7(1) | Training module is developed | EMIS database | TPDC/Ministry of Education and Science | Municipalities | IV quarter of 2024 | 90000 | 90000 | 32 06 04
|  |  |  | 1.1.1.7(2) | Over 50% of educator-pedagogues are trained
Objective 1.1.2: |  |  | Improving the learning environment and quality of teaching in early and preschool education institutions
Outcome indicator 1.1.2.1: |  |  | Remuneration of educators-pedagogues of early and preschool educational institutions |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science data
[6 empty] | Indicator | 336 GEL (national average 844 GEL) | An increase of at least 10% of the average monthly salary | An increase of at least 20% of the average monthly salary | Equal to the national average monthly salary
Risk: |  |  | Lack of human and financial resources
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
1.1.2.1 | Updating and confirming the state standards for early and preschool education |  |  | 1.1.2.1(1) | The state standard of early and preschool education and education is updated and confirmed | Resolution of the Government of Georgia | Ministry of Education and Science |  | IV quarter of 2022 | Administrative cost
1.1.2.2 | Preparation and approval of the evaluation plan for the evaluation of the educational program |  |  | 1.1.2.2(1) | The evluation plan for evaluating the educational program is developed and approved | Annual Report of the Ministry of Education and Science | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
1.1.2.3 | Conduct the training on early education curriculum - "Play" |  |  | 1.1.2.3(1) | Over 50% of educator-pedagogues are re-trained | EMIS database | Ministry of Education and Science | TPDC | IV quarter of 2023 | 36000 | 36000 | 32 02 13 03
1.1.2.4. | Development of a temporary regulation for authorization by an early childhood and preschool education institution, as well as for the suspension and termination of the institution's authorization |  |  | 1.1.2.4.(1) | Temporary regulation is submitted for confirmation | Initiated document | NCEQE/Ministry of Education and Science |  | IV quarter of 2022 | 6000 |  |  | 6000 | UNICEF
1.1.2.5. | Creation of a primary registration base for early and preschool care and education institutions |  |  | 1.1.2.5.(1) | Electronic registration database is created | Database of registered institutions | EMIS/Ministry of Education and Science | NCEQE; Ministry of Regional Development and Infrastructure | II quarter of 2022 | Administrative cost
1.1.2.6. | Implementation of self-assessment by registered early and preschool care and education institutions |  |  | 1.1.2.6.(1) | Number of registered early childhood and preschool care and education institutions that have submitted self-assessment reports | NCEQE Report | NCEQE /Ministry of Education and Science | Municipalities | IV quarter of 2023 | 850 000 | 850 000 | 32 01 03
1.1.2.7. | Approval of the schedule for the authorization of registered early and preschool care and education institutions |  |  | 1.1.2.7.(1) | Approved authorization schedule | Ministry of Education and Science | Ministry of Education and Science/NCEQE |  | IV quarter of 2024 | Administrative cost
Objective 1.1.3: |  |  | Promoting the involvement of the child's parents/representatives and the community in the activities of early and preschool educational institutions
Outcome indicator 1.1.3.1: |  |  | The share of early childhood and preschool institutions with parent/representative and community engagement policies |  |  |  | Basline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science data
[6 empty] | Indicator | 0 | >20 % | > 40 % | 100%
Risk: |  |  | Lack of human and financial resources, lack of consensus among stakeholders
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
1.1.3.1 | Conducting awareness-raising campaigns on the importance of early childhood education services, including gender equality issues |  |  | 1.1.3.1(1) | Minimuum 4 campaigns | Information campaign materials | Ministry of Education and Science | Municipalities | IV quarter of 2023 | 20000 |  |  | 20000 | UNICEF
1.1.3.2 | Development of training schemes and support materials for directors of early and preschool care and education institutions on parental involvement and communication |  |  | 1.1.3.2(1) | Training schemes and materials are developed | Annual Report of the Ministry of Education and Science | Ministry of Education and Science | HEIs | IV quarter of 2024 | Administrative cost
Sectoral priority 2 |  | An equitable, inclusive, and diverse education and science system
Goal 2.1: |  |  | Supporting the participation of disadvantaged children in early education and school readiness programs |  |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  | Goal 4 Quality education Goal 8 Decent work and economic growth
Impact indicator 2.1.1: |  |  | The share of disadvantaged children receiving special support |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2020 | 2025 | 2030 |  | Ministry of Education and Science data
[6 empty] | Indicator | 0 | >40 % | >70%
Objective 2.1.1: |  |  | Ensuring an inclusive, safe and holistic child development-oriented learning process in early and preschool education institutions
Outcome indicator 2.1.1.1: |  |  | The share of early and preschool education institutions in the total number where the practice of implementing inclusive education meets the modern quality requirements |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science data
[6 empty] | Indicator | 0 | >30 % | >70 % | 100%
Risk |  |  | The challenge of fully implementing the decision at the level of self-governments
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
2.1.1.1 | Development of educational resources for children with special educational needs |  |  | 2.1.1.1(1) | Educational resources have been developed for children with special educational needs | Annual Report of the Ministry of Education and Science | Ministry of Education and Science | HEIs | IV quarter of 2024 | 50000 |  |  | 50000 | UNICEF
2.1.1.2 | Development of a variety of multilingual resources |  |  | 2.1.1.2(1) | Learning resources for multilingual education have been prepared | Annual Report of the Ministry of Education and Science | Ministry of Education and Science |  | IV quarter of 2024 | 50000 |  |  | 50000 | UNICEF
Objective 2.1.2: |  |  | Development of targeted early and preschool education support services for disadvantaged children and children with special educational needs
Outcome indictor 2.1.2.1: |  |  | Number of children participating in school readiness programs one year before entering school |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[6 empty] | Indicator | 80% | 90% | 100% | 100%
Outcome indicator 2.1.2.2: |  |  | The share of children enrolled/identified in need of additional support in early and preschool education institutions |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[6 empty] | Indicator | N/A | 3% | 5% | 7%
Risk: |  |  | Challenges of collection and analysis of accurate and reliable data on children in risk groups; insufficient coordination between different branches of the government and municipalities
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
2.1.2.1 | Development of a monitoring system for the early detection of children in the risk group |  |  | 2.1.2.1(1) | A monitoring system for children in the risk group has been developed | Central and municipal register of children with special educational needs | Ministry of Internally Displaced Persons from the Occupied Territories, Health, Labour and Social Affairs of Georgia | Ministry of Education and Science, Municipalities | IV quarter of 2023 | Administrative cost
2.1.2.2 | Development of a policy document for the implementation of the school readiness program |  |  | 2.1.2.2(1) | Policy document has been developed | Annual Report of the Ministry of Education and Science | Ministry of Education and Science | Municipalities | IV quarter of 2023 | Administrative cost
2.1.2.3 | Conduct research to explore the reasons for children left behind early and preschool education |  |  | 2.1.2.3(1) | The research is conducte | Research Report | Ministry of Education and Science |  | IV quarter of 2023 | 50000 |  |  | 18000 | UNICEF | 32000
2.1.2.4 | Creation of regulations for the transition mechanism from family to kindergarten and from kindergarten to school |  |  | 2.1.2.4(1) | Regulations for transition mechanism has been created | Annual Report of the Ministry of Education and Science | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
Sectora priority 3 |  | System of management and accountability of education and science system
Goal 3.1: |  |  | Strengthening the effectiveness and sustainability of the early and preschool education system |  |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  | Goal 4 Quality education Goal 16 Peace, justice, and strong institutions
Impact indicator 3.1.1: |  |  | Share of children (2 to 5 years old) enrolled in early and preschool care and education institutions of the total number |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2021 | 2025 | 2030 |  | Education Management Information System (EMIS) data
[6 empty] | Indicator | 71% | 80% | 96%
Objective 3.1.1: |  |  | Ensuring access to updated early and preschool education and development
Outcome indicator 3.1.1.1: |  |  | The share of buildings of early and preschool education institutions renovated following the technical infrastructure regulation |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science data
[6 empty] | Indicator | N/A | 20% increase | 30% increase | 100%
Outcome indicator 3.1.1.2: |  |  | Number of providers of early and preschool education services |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science data
[6 empty] | Indicator | 1647 | 1700 | 1800 | 2100
Outcome indicator 3.1.1.3: |  |  | Child and educator-pedagogue ratio |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[6 empty] | Indicator | 17/1 | 15/1 | 15/1 ratio sustained | 15/1 ratio susutained
Risk |  |  | Lack of human and financial resources, lack of consensus among stakeholders
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
3.1.1.1 | Preparation of the concept of development and implementation of alternative models of preschool education |  |  | 3.1.1.1(1) | The concept of developing and implementing alternative models of preschool education has been prepared | Annual Report of the Ministry of Education and Science | Ministry of Education and Science | Municipalitites | IV quarter of 2023 | 50000 |  |  | 50000 | UNICEF
3.1.1.2 | Development of a national strategy on the social package and remuneration of early childhood and preschool teachers-pedagogues and submission for approval |  |  | 3.1.1.2(1) | The strategy is developed and submitted to the government for approval | Governent resolution | Ministry of Education and Science | Ministry of Finance, Ministry of Internally Displaced Persons from the Occupied Territories, Health, Labour and Social Affairs of Georgia | IV quarter of 2023 | Administrative cost
3.1.1.3 | Development of policies and guidelines for the career ladder system |  |  | 3.1.1.3(1) | Policies and guidelines have been developed | Annual Report of the Ministry of Education and Science | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
Abbreviations used in the Action Plan: EMIS - Education Management Information System; HEI - higher educational institutions; TPDC - Teachers' Professional Development Center; NCEQE - National Center for Education Quality Enhancement; UNICEF - United Nations Children's Fund.
* Note: the donor budget provided for in the action plan may change during the implementation period of the plan, and accordingly, depending on the need, the present action plan may be revised as well.

## General Education AP
Sectoral priority 1 |  | Quality and sustainable education and science systems focused on the needs of students, society, and the state
Goal 1.2: |  |  | Providing an accessible learning process for each student in general educational institutions, focused on high attainable results and holistic development of the student |  |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  |  | Goal 4 Quality education Goal 8 Decent work and economic growth
Impact indicator 1.2.1: |  |  | (1) Average student assessment scores in reading, math, and science (2) Percentage of sixth- and ninth-graders who meet the National Curriculum's minimum proficiency in (i) reading and (ii) math |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Final
[7 empty] | Year | 2018 | 2025 | 2030 |  | Georgia Program for International Student Assessment (PISA) report; Education Management Information System (EMIS) data
[7 empty] | Indicator | (1) Reading- 380; math- 398;science - 383. (2) Reading: 36 %, math - 39 % | (1) improvement of 2018 average points in each subject by 30 units +; (2) Not less than 50% in each subject | (1) improvement of 2018 average points in each subject by 60 units +; (2) Not less than 70% in each subject
Objective 1.2.1: |  |  | Improving the qualifications of teachers and principals and providing needs-based continuous professional development
Outcome indicator 1.2.1.1: |  |  | The share of teachers who successfully meet the intermediate and higher level requirements defined by the new teacher evaluation system |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Interim | Final
[7 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[7 empty] | Indicator | N/A | 30% | 50% | 70%
Outcome indicator 1.2.1.2: |  |  | Share of certified directors in the total number |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Interim | Final
[7 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[7 empty] | Indicator | N/A | 30% | 40% | 70%
Risk: |  |  | Lack of human and financial resources
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
1.2.1.1 | Updating the teacher's professional standards and field characteristics |  |  | 1.2.1.1(1) | The teachers professional standard is updated | Respective resoltion by Minister/Deputy Minister | Ministry of Education and Science/TPDC/NCEQE |  | IV quarter of 2023 | 300000 |  |  | 300000 | World Bank; UNICEF
1.2.1.2 | Updating the content of teacher education programs of higher educational institutions |  |  | 1.2.1.2(1) | The content of teacher education programs of higher educational institutions is updated | Updated syllabi for teacher training programs | Ministry odf Education and Science/NCEQE/TPDC |  | IV quarter of 2023 | Administrative cost
1.2.1.3 | External targeted assessment of higher educational institutions implementing basic teacher education programs based on new teacher standards |  |  | 1.2.1.3(1) | Teacher education programs are evaluated based on external evaluation | NCEQE Report on HEI evalation | Ministry of Education and Science/NCEQE |  | IV quarter of 2024 | Administrative cost
1.2.1.4 | Development and approval of the induction program for newly qualified teachers |  |  | 1.2.1.4(1) | The induction program for newly qualified teachers is developed and approved | Respective Resoltion by Minister/Deputy Minister | Ministry of Education and Science/TPDC |  | IV quarter of 2023 | Administrative cost
1.2.1.5 | Development and approval of the appropriate policy document for the attraction and employment of tea |  |  | 1.2.1.5(1) | A policy document for attracting and employing teachers has been developed and approved | Respective Resoltion by Minister/Deputy Minister | Ministry of Education and Science/TPDC |  | IV quarter of 2023 | Administrative cost
1.2.1.6 | Updating and approving the system of teachers' professional skills and career advancement |  |  | 1.2.1.6(1) | A new scheme of professional development and career advancement for teachers has been developed and approved | Respective Resoltion by Minister | Ministry of Education and Science/TPDC |  | IV quarter of 2022 | Administrative cost
1.2.1.7 | Development and piloting of a methodological guide for school democratic governance |  |  | 1.2.1.7(1) | A methodological manual for democratic school governance has been developed; Piloted in 20 schools | Methodological guide; Annual Report of the Ministry of Education and Science | Ministry of Education and Science |  | IV quarter of 2023 | 135000 |  |  | 135000 | CoE
1.2.1.8 | Selection and training of a new stream of school principals |  |  | 1.2.1.8(1) | All principals of the new stream school have been selected and trained following the updated requirements | EMIS data | Ministry of Education and Science/NCEQE/EMIS |  | IV quarter of 2023 | Administrative cost
1.2.1.9 | Developing a professional development program for school principals and teachers on democratic school governance and training staff in pilot schools |  |  | 1.2.1.9(1) | A professional development program has been developed for school principals and teachers on democratic school governance; 25 school principals and teachers have been trained | Professional development program; attendance sheets | Ministry of Education and Science |  | IV quarter of 2023 | 55000 |  |  | 55000 | CoE
1.2.1.10 | Involvement of teachers from the occupied Gali district in developing a new scheme for teachers' professional development and career advancement; customizing professional development plan to the needs. |  |  | 1.2.1.10(1) | The professional development plan is developed | Annual Report of the Ministry of Education and Science | TPDC/ Ministry of Education and Science | Ministry of Education and Culture of Abkhazia | IV quarter of 2023 | Administrative cost
Objective 1.2.2: |  |  | Creating a favorable environment for learning and teaching in general educational institutions and providing them with diverse modern resources
Outcome indicator 1.2.2.1: |  |  | The share of schools meeting the standard for school accreditation |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[6 empty] | Indicator | N/A | 20% | 30% | 80%
Outcome indicator 1.2.2.2: |  |  | Number of digital learning resources by grade and subject |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Annual Report of the Ministry of Education and Science
[6 empty] | Indicator | N/A | 2 in each classroom | LAB on the wheel on each floor of schools | 4 in each classroom
Outcome indicator 1.2.2.3: |  |  | a) The share of students who report being satisfied with the learning process (1) national average, (2) high-achievement students according to SES, (3) students below the baseline level of achievement according to SES; b) The share of students who report that they have a sense of belonging to the school |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2018 | 2024 | 2027 | 2030 | Program for International Student Assessment Georgia (PISA) report based on the student questionnaire
[6 empty] | Indicator | a) (1) 7.56 % (2) 47.4% (3) 33% (b) 56% | (a) (1) 10 % (2) 40 %, (3) 40 % (b) 60 % | (a) (1) 15 % (2) 60 %, (3) 45 % (b) 70 % | (a) (1)20 %(2) 70 %, (3) 60 % (b) 80 %
Risk: |  |  | Lack of experience in creating digital resources, lack of financial resources
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
1.2.2.1 | Revise school accreditation standards, prioritizing the quality of learning and teaching resources |  |  | 1.2.2.1(1) | Athorization standard has been updated | NCEQE Report | Ministry of Education and Science/NCEQE |  | IV quarter of 2022 | 944000 | 944000 | 32 01 03
1.2.2.2 | Creating a plan for the purchase of additional materials/teaching resources based on the inventory survey of existing materials |  |  | 1.2.2.2(1) | Materials purchase plan | EMIS data | EMIS/Ministry of Education and Science/NCEQE |  | IV quarter of 2022 | Administrative cost
1.2.2.3 | Updating textbook standards and selection criteria |  |  | 1.2.2.3(1) | Standard and selection criteria of textbooks have been updated | Revised regulation of textbook evaluation | Ministry of Education and Science/EMIS |  | I quarter of 2022 | Administrative cost
1.2.2.4 | Creating new textbooks based on updated standards |  |  | 1.2.2.4(1) | Textbooks for secondary level in all compulsory subjects of X-XI-XII grades are created | Ministry of Education and Science data | Ministry oof Education and Science/EMIS/ESIDA |  | IV quarter of 2024 | 55400000 | 55400000 | 32 02 06 01 32 02 06 02
1.2.2.5 | Creating an electronic teaching-learning management system to ensure the availability of digital adaptive learning materi |  |  | 1.2.2.5(1) | An electronic teaching-learning management system has been created | Digital platform | Ministry of Education and Science | HEIs | III quarter of 2024 | 2500000 |  |  | 2500000 | World Bank
1.2.2.6 | Inventory survey of the school's physical infrastructure and development of a rehabilitation plan |  |  | 1.2.2.6(1) | Inventory of the school's physical infrastructure rehabilitation plan is developed | Inventory survey report | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
1.2.2.7 | Training and retraining of ERC specialists, school principals, and teachers in the implementation of personal education programs |  |  | 1.2.2.7(1) | ERC specialists, school principals, and teachers have been trained | Ministry of Education and Science Report | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
1.2.2.8 | Creating a safe and positive environment and monitoring plan in schools, following respective indicators |  |  | 1.2.2.8(1) | A concept and action plan focused on strengthening the safety and positive learning environment of schools has been created | Resolution by Minister/Deputy Minister | Ministry of Education and Science/NCEQE |  | IV quarter of 2023 | Administrative cost
1.2.2.9 | Establishing a national grant system for the development of new student assessment tools and methodological materials |  |  | 1.2.2.9(1) | Assessment methodology and tools (including assessment of general competencies) are defined; A national grant is defined | Ministers Decree | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
1.2.2.10 | Implementation of the third-generation national curriculum |  |  | 1.2.2.10(1) | The third-generation national curriculum is developed | EMIS database; national curriculum monitoring report | Ministry of Education and Science |  | IV quarter of 2023 | 16600000 | 16600000 | 32 02 13 01
1.2.2.11 | Creation of new methodology, materials and training programs for teachers |  |  | 1.2.2.11(1) | A new methodology, materials, and training programs have been created for teachers | Ministry of Education and Science webpage | Ministry of Education and Science/TPDC | HEIs | IV quarter of 2023 | Administrative cost
1.2.2.12 | Completion of the preparatory stage of the European school project implementation |  |  | 1.2.2.12(1) | The preparatory stage of the European school project is completed | Annual Report of the Ministry of Education and Science | Ministry of Education and Science |  | III quarter of 2023 | 50 000 000 | 40 000 000 | 32 07 01 | 10 000 000 | EU
Objective 1.2.3 |  |  | Increasing the involvement of parents/representatives in school life and the teaching-learning process
Outcome indicator 1.2.3.1: |  |  | The share of parents who participated in the following activities: (1) discussed their child's progress with at least one subject teacher on their initiative; (2) discussed the child's progress with at least one subject teacher at the teacher's initiative; (3) participated in the self-governance of the school; (4) volunteered in school, physical activity, and/or other extracurricular activities |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Interim | Final
[7 empty] | Year | 2018 | 2024 | 2027 | 2030 | PISA Georgia Report prepared by the National Assessment and Examination Center or the Organization for Economic Development and Cooperation (OECD) based on the Principal's Questionnaire
[7 empty] | Indicator | (1) 52 %, (2) 49 %; (3) 23%, (4) 24 % | (1) 55 %, (2) 60 %; (3) 27%, (4) 270 % | (1) 60 %, (2) 70 %; (3) 30%, (4) 30 % | (1) 70 %, (2) 80 %; (3) 40%, (4) 40 %
Risk: |  |  | Low readiness of schools, low interest of parents
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
1.2.3.1 | Development of an effective concept of school-parent partnership and guidance materials |  |  | 1.2.3.1(1) | Concept and guidance materials are developed | Ministry of Education and Science ebpage | Ministry of Education and Science |  | IV quarter of 2022 | 150000 |  |  | 150000 | UNICEF
1.2.3.2 | Training of leaders (principals / ERC / or representatives of self-governments) to start a comprehensive program of parental involvement |  |  | 1.2.3.2(1) | Most of the leaders have been trained in the comprehensive program of parental involvement | EMIS database | Municipalities | Ministry of Education and Science | IV quarter of 2023 | Administrative cost
Sectoral priority 2 |  | An equitable, inclusive, and diverse education and science system
Goal 2.2: |  |  | Creating equal opportunities for learning and development for every student at all levels of general education |  |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  |  | Goal 4 Quality education Goal 8 Decent work and economic growth
Impact indicator 2.2.1: |  |  | Indicators of receiving education in vulnerable groups: (1) rural school students; (2) ethnically non-Georgian students (in Azerbaijani and Armenian schools); (3) disadvantaged students (low welfare quintile) |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Final
[7 empty] | Year | 2018 | 2025 | 2030 |  | Education Management Information System (EMIS) database; MICS GEORGIA
[7 empty] | Indicator | School attendence data: village - 82.7% Azerbaijani - 59.6% Armenian - 72.1% disadvantaged - 73.7% | Improvement of the baseline data in each sector to 85% | Improvement of the baseline data in each sector to 95%
Impact indicator 2.2.2: |  |  | The share of disadvantaged pupils in the top attainment level (top quartile) |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Final
[7 empty] | Year | 2018 | 2025 | 2030 |  | The PISA Georgia report prepared by the National Assessment and Examinations Center or the Organization for Economic Development and Cooperation (OECD).
[7 empty] | Indicator | 12,3% | 20% | 30%
Objective 2.2.1: |  |  | Raising the qualifications of special teachers and support staff and developing inclusive teaching competencies
Outcome indicator 2.2.1.1: |  |  | The share of student teachers who have successfully completed at least one course/module on inclusive education (including bilingual education, working with students, etc.) |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Interim | Final
[7 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[7 empty] | Indicator | N/A | 30% | 50% | 100%
Outcome indicator 2.2.1.2: |  |  | Number of special education teachers graduating from teacher training programs (bachelor's or master's level) |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Interim | Final
[7 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[7 empty] | Indicator | N/A | 40 | 50 | 200
Risk: |  |  | Insuufficient readiness of teachers and HEIs
Activities |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
2.2.1.1 | Development and integration of inclusive education modules in all teacher education programs |  |  | 2.2.1.1(1) | The principle of inclusive education is included in all teacher education programs | NCEQE database; TPDC training modules | Ministry of Education and Science/TPDC |  | IV quarter of 2023 | 300000 |  |  | 300000 | UNICEF
2.2.1.2 | Development of inclusive education modules/programs for further professional development of teachers |  |  | 2.2.1.2(1) | Updated inclusive education programs have been created for the further professional development of teachers | TPDC training modules; Ministry of Education and Science webpage | Ministry of Education and Science/TPDC |  | IV quarter of 2023 | 1250000 | 1250000 | 32 06 04
Objecttive 2.2.2: |  |  | Creating an appropriate learning environment for special educational needs in general educational institutions and providing access to quality learning resources for each student
Outcome indicatoor indicator 2.2.2.1: |  |  | The percentage of schools that have adapted educational infrastructure for students with special educational needs: 1) partially adapted; 2) fully adapted |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Interim | Final
[7 empty] | Year | 2019 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[7 empty] | Indicator | (1) 30 % (690 schools); (2) 5 % (120 scools) | (1) >40 % ; (2) >10% | (1) >60 % ; (2) >20% | (1) >90 % ; (2) >50%
Outcome indicator 2.2.2.2: |  |  | A general education budget earmarked for the development of adaptive and other support resources |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Interim | Final
[7 empty] | Year | 2021 | 2024 | 2027 | 2030 | Budget of the Ministry of Education and Science
[7 empty] | Indicator | 471300 | 5%- increase | 10%-increase | 15%-increase
Risk: |  |  | Lack of material and financial resources
Activity |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
2.2.2.1 | Assessment of learning process losses during the pandemic and development of a plan to eliminate differences between achievement in different groups of students |  |  | 2.2.2.1(1) | An analysis of educational losses has been completed, and a plan for their elimination has been developed | Ministry of Education and Science webpage | Ministry of Education and Science |  | IV quarter of 2022 | Administrative cost
2.2.2.2 | Development of tools for returning students to formal education |  |  | 2.2.2.2(1) | Tools have been developed to help students return to formal education | Respective Decree by the Minister/Deputy Minister | Ministry of Education and Science |  | IV quarter of 2022 | 300000 |  |  | 300000 | UNICEF
2.2.2.3 | Development of an individual curriculum for all students with individual needs |  |  | 2.2.2.3(1) | Following the requirements of the national curriculum of the third generation, individual plans have been prepared for all students with the status of SEN | EMIS data | Ministry of Education and Sciecne |  | IV quarter of 2023 | Administrative cost
2.2.2.4 | Implementation of bilingual education programs in non-Georgian language schools |  |  | 2.2.2.4(1) | Bilingual educational programs are implemented in schools for ethnic minorities | NCEQE Report | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
2.2.2.5 | Development and implementation of special programs for students with special needs (hearing and vision impairment, simplified training programs, etc.) |  |  | 2.2.2.5(1) | A national program for supporting students with special needs (hearing and vision impairment) has been developed and implemented | NCEQE Report | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
2.2.2.6 | Translation of new textbooks for non-Georgian language schools according to the third-generation national curriculum |  |  | 2.2.2.6(1) | Textbooks created according to the third-generation national curriculum have been translated for non-Georgian language schools | Ministry of Education and Science webpage | Ministry of Education and Science/EMIS/ESIDA |  | IV quarter of 2023 | 55000 | 55000 | 32 02 06 01 32 02 06 02
Sectoral priority 3 |  |  | System of management and accountability of education and science system
Goal 3.2: |  |  | Improving the effectiveness and sustainability of the management of the general educational institution |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  |  | Goal 4 Quality education Goal 16 Peace, justice, and strong institutions
Impact indicator 3.2.1: |  |  | The share of students with equal and diverse learning opportunities: (a) in rural areas; (b) in urban areas |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2021 | 2025 | 2030 |  | Education Management Information System (EMIS) data; National Center for Education Quality Enhancement data
[6 empty] | Indicator | N/A | (a) >80 % (b) >60 % | (a) >95 % (b) >90 %
Impact indicator 3.2.2: |  |  | The share of authorized schools meeting infrastructure standards |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2021 | 2025 | 2030 |  | National Center for Education Quality Enhancement data
[6 empty] | Indicator | N/A | > 70 % | > 95%
Objective 3.2.1: |  |  | Development of monitoring and evaluation system for general educational institutions
Outcome indicator 3.2.1.1: |  |  | The share of general education institutions with a proper system of monitoring and evaluation in the total number |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2018 | 2024 | 2027 | 2030 | National Assessment and Examination Center or Organization for Economic Cooperation Development (OECD) based on PISA report
[6 empty] | Indicator | Based on PISA 2018 results (SC037, consisting of 10 points), minimum 1 correct answer to questions ny 49% of school directors | > 60 % | > 80 % | > 95%
Outcome indicator 3.2.1.2: |  |  | The share of schools with a comprehensive database updated annually (including information on student demographics, student performance, teacher characteristics, extracurricular programs, infrastructure, etc.) |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[6 empty] | Indicator | N/A | > 80% | > 90% | > 95%
Risk: |  |  | The potential risk of new methodology obscurity. Lack of systematic approaches and consistency in the implementation process.
Activity |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
3.2.1.1 | Developing a school system restructuring plan |  |  | 3.2.1.1(1) | A school system restructuring plan has been developed | Respective Decree by the Minister/Deputy Minister | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
3.2.1.2 | Creating a plan for implementing the school regional management model |  |  | 3.2.1.2(1) | The plan for implementing the school regional governance model has been created | Respective Decree by the Minister/Deputy Minister | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
3.2.1.3 | Creation of a new school financing system |  |  | 3.2.1.3(1) | A new school financing system has been created | Respective Decree by the Minister | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
3.2.1.4 | Creation of a new model of teachers' remuneration system |  |  | 3.2.1.4(1) | A new teachers' remuneration system has been created | Respective Decree by the Minister | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
3.2.1.5 | Developing a strategy and a new model for school management improvement |  |  | 3.2.1.5(1) | A school management improvement strategy and a new model have been developed | Respective Decree by the Minister/Deputy Minister | Ministry of Education and Science |  | IV quarter of 2022 | 12000 |  |  | 12000 | World Bank
3.2.1.6 | Creating school districts with new roles and responsibilities in line with the new school management model |  |  | 3.2.1.6(1) | School districts are created at the level of resource centers | EMIS data | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
3.2.1.7 | Implementation of the school authorization system |  |  | 3.2.1.7(1) | The number of authorized schools within the framework of the implementation of the school authorization system | NCEQE materials | NCEQE/Ministry of Education and Science |  | IV quarter of 2023 | 1844000 | 1844000 | 32 01 03
3.2.1.8 | Development and updating of policies, and mechanisms for certification, recruitment, and career development of school principals |  |  | 3.2.1.8(1) | Policies and mechanisms for certification and career development of school principals have been developed and updated | Respective Decree by the Minister/Deputy Minister | Ministry of Education and Science/NAEC, TPDC |  | IV quarter of 2023 | 98000 |  |  | 98000 | World Ban
3.2.1.9 | Developing a school support system to hold schools accountable for student achievement (national or regional-level subject-specific tests) and to ensure student well-being and motivation |  |  | 3.2.1.9(1) | A school support system has been created to support the student-centered learning process | Respective Decree by the Minister/Deputy Minister | Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
Abbreviations uused in Action Plan: NCEQE - LEPL National Center for Education Quality Enhancement; TPTC - Teachers Proffessional Development Center; EMIS - Education Management Information System; ESIDA - Education and Science Infrastructure Development Agency; NAEC- National Assessment Examination Center; ERC - Educational Resource Center; EU- European Union; UNICEF - United Nations International Child Federation; CoE- Council of Europe.
* Note: the donor budget provided for in the action plan may change during the implementation, and accordingly, depending on the need, the current action plan may be revised.

## VET AP
Sectoral priority 1 |  | Quality and sustainable education and science systems focused on the needs of students, society, and the state
Goal 1.3: |  |  | Development of an innovative and flexible vocational education system focused on the needs of society and economy | [7 empty] | Linkages with the Sustainable Development Goals (SDG): |  |  | Goal 4. Quality education Goal 8. Decent work and economic growth
Impact indicator 1.3.1: |  |  | The share of those enrolled in vocational education programs who dropped out |  | Baseline | Target |  |  |  |  | Source of verification
[6 empty] | Interim | Final
|  |  |  | Year | 2021 | 2025 | 2030 |  |  |  | Education Management Information System (EMIS) data
|  |  |  | Indicator | 33% | 30% | 23%
Impact indicator 1.3.2: |  |  | The employment rate of vocational education graduates |  | Baseline | Target |  |  |  |  | Source of verification
[6 empty] | Interim | Final
|  |  |  | Year | 2020 | 2025 | 2030 |  |  |  | Tracer study of vocational education alumni
|  |  |  | Indicator | 49% | 62% | 70%
Objective 1.3.1: |  |  | Equipping vocational education students/listeners with the necessary skills and competencies for continuous employment in the local and international labor market
Outcome indicator1.3.1.1: |  |  | Number of graduates of dual programs |  | Baseline | Target |  |  |  |  | Source of verification
[6 empty] | Interim | Interim | Final
|  |  |  | Year | 2021 | 2024 | 2027 | 2030 |  |  | Education Management Information System (EMIS) data
|  |  |  | Indicator | 332 | 600 | 1000 | 2000
Outcome indicator 1.3.1.2: |  |  | Indicator of self-employment/entrepreneurial activity of vocational education graduates |  | Baseline | Target |  |  |  |  | Source of verification
[6 empty] | Interim | Interim | Final
|  |  |  | Year | 2021 | 2024 | 2027 | 2030 |  |  | Tracer study of vocational education alumni
|  |  |  | Indicator | 10% | 12% | 18% | 22%
Risk: |  |  | The low index of private sector involvement; Lack of financial resources
Activities |  |  |  | Output indicator |  |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[12 empty] | State budget |  | Other |  | Deficit
[12 empty] | Amount | Program code | Amount | Organization
1.3.1.1 | Updating the methodology of elaborating vocational qualifications and developing the rule of the occupational standard |  |  | 1.3.1.1 (1) | The methodological document for qualification has been elaborated; The rule for the development of the occupational standard has been developed |  | Updated methodology for the development of vocational qualifications and rule of occupational standard development | Skills Agency/ Ministry of Education and Science |  | IV quarter of 2022 | Administrative cost
1.3.1.2 | Introduce a diverse mechanism of international mobility |  |  | 1.3.1.2 (1) | Various mechanisms of international mobility of students and staff have been introduced |  | Report of Skills Agency | Skills Agency/ Ministry of Education and Science |  | IV quarter of 2023 | 200 000.00 | 200 000.00 | 32 03 02
1.3.1.3 | Approval and implementation of the rule of work-based learning implementation and the rule of obtaining the status of a teaching enterprise |  |  | 1.3.1.3 (1) | The rule of implementation work-based learning and the rule of obtaining the status of a teaching enterprise has been approved |  | The rule of implementation work-based learning and the rule of obtaining the status of a teaching enterprise | Skills Agency/ Ministry of Education and Science | VEIs | IV quarter of 2022 | Administrative cost
1.3.1.4 | Increase the scale of integrated programs |  |  | 1.3.1.4 (1) | All public vocational educational institutions implement integrated vocational educational programs |  | The decision of the Authorization Council | Skills Agency/ Ministry of Education and Science | VEIs | IV quarter of 2024 | 5100000 | 5000000 | 32 03 01 32 03 02 | 100000 | UNDP
1.3.1.5 | Increasing the scale of vocational training/retraining programs |  |  | 1.3.1.5 (1) | Number of vocational training and retraining programs |  | The decision of the Authorization Council | Skills Agency/ Ministry of Education and Science |  | IV quarter of 2024 | 9400000 | 9400000 | 32 03 02
1.3.1.6 | Preparation of analysis of approaches related to key competencies |  |  | 1.3.1.6 (1) | An analysis and relevant recommendations have been prepared regarding key competencies |  | The document of analysis | Skills Agency/ Ministry of Education and Science |  | IV quarter of 2024 | 300 000 |  |  | 300 000 | EU
1.3.1.7 | Introduction of a new module of civic education |  |  | 1.3.1.7 (1) | A new civic education module has been introduced within all vocational education programs |  | New module of Civic Education | Skills Agency/Ministry of Education and Science/National Center for Education Quality Enhancement | VEIs | IV quarter of 2024 | 400 000 |  |  | 400 000 | EU
1.3.1.8 | Introduction of an updated entrepreneurial education module |  |  | 1.3.1.8 (1) | An updated entrepreneurial education module has been intoduced within all vocational education programs |  | Updated entrepreneurial education module | Skills Agency/ Ministry of Education and Science | VEIs | IV quarter of 2023 | 200000 | 100000 | 32 03 02 | 100000 | UNDP
1.3.1.9 | Preparing the concept of digital competencies |  |  | 1.3.1.9 (1) | The concept of the development of digital competencies has been prepared |  | The concept of digital competencies development | Skills Agency/ Ministry of Education and Science | VEIs |  | 50 000 |  |  | 50 000 | EU
1.3.1.10 | Elaborating policies to strengthen foreign language teaching |  |  | 1.3.1.10 (1) | A document on the modern approach to teaching foreign languages has been developed |  | Policy paper | Skills Agency/ Ministry of Education and Science | VEIs | IV quarter of 2023 | 100000 | 100000 | 32 03 02
1.3.1.11 | Development of educational resources for vocational education programs |  |  | 1.3.1.11 (1) | At least 10 resources, including a minimum of 2 digital are developed to support the programs |  | The developed resources | Skills Agency/ Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
1.3.1.12 | Updating the system of quality assurance of vocational education based on the new authorization standard and EQAVET indicators |  |  | 1.3.1.12 (1) | At least 20 vocational educational institutions are authorized under the new authorization standard |  | Decisions of the Authorization Council; analysis document | LEPL National Center for Education Quality Enhancement/EMIS | VEIs | IV quarter of 2024 | Administrative cost
|  |  |  | 1.3.1.12 (2) | Evaluation of the vocational education quality has been carried out using the indicators of the European network (EQAVET)
1.3.1.13 | Implementation of self-assessment mechanism for Vocational Education Institutions (VEIs) |  |  | 1.3.1.13 (1) | Institutional self-assessment mechanisms have been implemented in all vocational educational institutions |  | Annual report of the Skills Agency | Skills Agency/ Ministry of Education and Science | VEIs | IV quarter of 2024 | Administrative cost
1.3.1.14 | Establishment of sectoral networks of vocational educational institutions |  |  | 1.3.1.14 (1) | At least 3 sectoral networks are developed |  | Annual report of the Skills Agency | Skills Agency/ Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
Objective 1.3.2: |  |  | Promotion of continuous professional development of vocational education teachers
Outcome indictor1.3.2.1: |  |  | The share of teachers who benefit from professional development services offered at the vocational education institutions |  | Baseline | Target |  |  | Source of verification
[6 empty] | Interim | Interim | Final
|  |  |  | Year | 2021 | 2024 | 2027 | 2030 | Skills Agency's/Vocational Education Institutions data
|  |  |  | Indicator | 0 | 50% | 80% | 100%
Risk: |  |  | The lack of financial resources, delay in the approval of the regulatory framework; Low interest of teachers
Activities |  |  |  | Output indicator |  |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[12 empty] | State budget |  | Other |  | Deficit
[12 empty] | Amount | Program code | Amount | Organization
1.3.2.1 | Development of a teachers continuous professional development framework |  |  | 1.3.2.1(1) | The regulatory framework for the continuous professional development of teachers has been developed and approved |  | Regulatory acts | Skills Agency/ Ministry of Education and Science |  | IV quarter of 2023 | 500000 | 500000 | 32 03 02
1.3.2.2 | Support introduction of the teachers continuous professional development model |  |  | 1.3.2.2(2) | The teachers continuous professional development model for teachers has been piloted in 10 public vocational educational institutions |  | Pilot report | Skills Agency/ Ministry of Education and Science |  | IV quarter of 2024 | 200 000 | 200 000 | 32 03 02
Sectoral priority 2 |  |  | An equitable, inclusive, and diverse education and science system
Goal 2.3: |  |  | Providing access to diverse, inclusive, and individual needs-oriented vocational education | [5 empty] | Linkages with the Sustainable Development Goals (SDG): |  |  |  | Goal 4. Quality education Goal 8. Decent work and economic growth
Impact indicator 2.3.1: |  |  | The number of students enrolled in vocational educational programs | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Inetrim | Final
[8 empty] | Year | 2021 | 2025 | 2030 |  | Education Management Information System (EMIS) data
[8 empty] | Indicator | 15000 | 21000 | 70 000
Impact indicator 2.3.2: |  |  | The number of municipalities with public vocational education institutions | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Final
[8 empty] | Year | 2021 | 2025 | 2030 |  | Annual Report of the Ministry of Education and Science of Georgia
[8 empty] | Indicator | 37 | 55 | All municipalities
Objective 2.3.1: |  |  | Enhancing lifelong learning opportunities through a flexible network of innovative, diverse and inclusive vocational education institutions
Outcome indicator 2.3.1.1: |  |  | Transition rate from general education institution to vocational education institutions of persons with special educational needs with basic education and complete general education | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Interim | Final
[8 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[8 empty] | Indicator | 105 | 150 | 300 | 400
Outcome indicator2.3.1.2 |  |  | Transition rate from general education institution to vocational education institutions of persons with basic education and complete general education | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Interim | Final
[8 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[8 empty] | Indicator | 1% with Basic Education; 3.6% with General Education | 2% with Basic Education; 5% with General Education | 8% with Basic Education; 10% with General Education | 10% with Basic Education; 12% with General Education
Risk: |  |  | Low level of awareness; lack of financial resources; less interest of educational institutions in innovative approaches and innovations
Activities |  |  |  | Output indicator |  |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[12 empty] | State budget |  | Other |  | Deficit
[12 empty] | Amount | Program code | Amount | Organization
2.3.1.1 | Development of a concept and conduction of an analysis for evaluating the effectiveness of vocational education services | სისტემის ეფექტიანობის ანალიზი | სისტემის ეფექტიანობის ანალიზი | 2.3.1.1(1) | A service evaluation concept has been developed, and research/analysis has been conducted |  | Concept; Annual Report | Skills Agency/ National Center for Education Quality Enhancement |  | IV quarter of 2024 | Administrative cost
2.3.1.2 | Assessment of national, regional, and sectoral needs and development of an expansion plan |  |  | 2.3.1.2(1) | The 2023-2025 expansion plan has been developed following the identified needs |  | The 2023-2025 expansion plan elaborated upon the identified needs | Skills Agency/Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
2.3.1.3 | Development of new educational institutions in accordance with the expansion plan |  |  | 2.3.1.3 (1) | At least 10 new educational institutions are developed, including those established with the public-private partnership |  | The decision of the Authorization Council; Project Report | Skills Agency/Ministry of Education and Science |  | IV quarter of 2024 | 105 000 000 | 30 000 000.00 | 32 07 02 | 75 000 000 | ADB
|  |  |  | 2.3.1.3 (2) | The implementation of vocational education programs is initiated in at least 20 public general education institutions
2.3.1.4 | Support the development of the Center of Excellence (CoE) |  |  | 2.3.1.4 (1) | Project/s to develop at least 3 Centers of Excellence have been started |  | Project Report | Ministry of Education and Science/Skills Agency |  | IV quarter of 2024 | 75 000 000 |  |  | 75 000 000 | KFW
2.3.1.5 | Support the development of regional hubs |  |  | 2.3.1.5 (1) | At least 2 regional hubs are established |  | Report of Skills Agency | Ministry of Education and Science/Skills Agency |  | IV quarter of 2024 | 6960000 |  |  | 6960000 | ADB
2.3.1.6 | Development and implementation of the action plan for the promotion of vocational education |  |  | 2.3.1.6(1) | The action plan for the promotion of vocational education has been developed and implemented |  | Promotion action plan; Skills Agency Report | Skills Agency/Ministry of Education and Science | VEIs | IV quarter of 2024 | 500000 | 500000 | 32 03 02
2.3.1.7 | Support service providers to improve access to the service of recognition of non-formal education |  |  | 2.3.1.7 (1) | A guideline for supporting service providers and for providing consultations is developed, relevant support/consultations are provided |  | Relevant guide; Skills Agency Report | Skills Agency/Ministry of Education and Science |  | IV quarter of 2023 | 210 000 | 210 000 | 32 03 02
2.3.1.8 | Introduction of inclusive services to support the participation of vulnerable groups in vocational education |  |  | 2.3.1.8(1) | At least 3 support services are introduced to support vulnerable groups |  | Report of Skills Agency | Skills Agency/Ministry of Education and Science | VEIs | IV quarter of 2024 | 800000 | 800000 | 32 03 02
2.3.1.9 | Development of career services in vocational education |  |  | 2.3.1.9(1) | Student and pre-student career guidance mechanisms have been developed at the vocational education level |  | Career guidance mechanisms | Skills Agency/Ministry of Education and Science | VEIs | IV quarter of 2024 | 7500000 | 7500000 | 32 03 02
|  |  |  | 2.3.1.9(2) | Vocational education services have been introduced at the basic and secondary levels of general education |  | Skills Agency
2.3.1.10 | Analysis of gender equality issues in the field of vocational education |  |  | 2.3.1.10 (1) | The issues of gender equality are analysed in the context of entering vocational education system, study process, and in the process of issuing qualification |  | Skills Agency | Skills Agency/Ministry of Education and Science |  | IV quarter of 2023 | Administrative cost
2.3.1.11 | Development/approval of the regulatory framework of the new model of state language teaching and its implementation |  |  | 2.3.1.11 (1) | The regulatory framework of the state language teaching program has been approved, and the introduction of a new model of teaching has begun |  | Regulations on the program implementation, enrollment, and financing procedures are put into effect | Skills Agency/Ministry of Education and Science | Educational institutions | IV quarter of 2023 | 100000 | 100000 | 32 03 02
Sectoral priority 3 |  |  | Management and accountability system of education and science system
Goal 3.3: |  |  | Enhancing the efficiency of the vocational education system |  |  |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  | Goal 4. Quality education Goal 8. Decent work and economic growth
Impact indicator 3.3.1: |  |  | Number of sectoral skills organizations |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Final
[7 empty] | Year | 2021 | 2025 | 2030 |  | Skills Agency's Report/Register of SSOs
[7 empty] | Indicator | 0 | 3 | 6
Objective 3.3.1: |  |  | Sharing responsibility for creating and implementing vocational education policy between public and private sectors
Outcome indicator 3.3.1.1: |  |  | Employer satisfaction index |  |  |  |  | Baseline | Target |  |  | Source of verification
[9 empty] | Interim | Interim | Final
[7 empty] | Year | 2021 | 2024 | 2027 | 2030 | Research Report
[7 empty] | Indicator | N/A | To be defined after the research | To be defined after the research | To be defined after the research
Risk: |  |  | Low rate of participation of parties involved in the new model of vocational education management
Activities |  |  |  | Output indicator |  |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[12 empty] | State budget |  | Other |  | Deficit
[12 empty] | Amount | Program code | Amount | Organization
3.3.1.1 | Revision and initiation of the regulatory framework of vocational education to support the introduction of new approaches in the vocational education management |  |  | 3.3.1.1(1) | Changes to the law on Vocational Education and respective by-laws have been developed and submitted for approval |  | Legislative changes/Decrees/Resolutions | Ministry of Education and Science/Skills Agency |  | I quarter of 2023 | Administrative cost
3.3.1.2 | Support development of Sectoral Skills Organizations (SSO) in order to develop participatory mechanisms of vocational education management |  |  | 3.3.1.2 (1) | The regulatory framework for SSOs development has been developed, and the activities of SSOs are supported, including new qualifications development |  | Skills Agency Report | Skills Agency/Ministry of Education and Science |  | IV quarter of 2024 | 2622000 | 2622000 | 32 03 02
3.3.1.3 | Support implementation of the best international practices for skills development |  |  | 3.3.1.3 (1) | At least 3 public and private actors of the vocational education system are members and actively cooperate with leading international organizations in the field |  | Skills Agency Report | Skills Agency/Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
3.3.1.4 | Development of an digital coordination platform |  |  | 3.3.1.4 (1) | An digital platform for efficient cooperation with donors has been introduced |  | Digital Coordination Platform |  |  | IV quarter of 2022 | Administrative cost
3.3.1.5 | Development and implementation of a new funding mechanism |  |  | 3.3.1.5 (1) | A new mechanism for funding vocational education has been developed |  | Respective Resolution | Skills Agency/Ministry of Education and Science |  | IV quarter of 2024 | 300000 |  |  | 300000 | GIZ
|  |  |  | 3.3.1.5(2) | New funding mechanisms have been introduced, including a performance-based funding component and a revised teacher remuneration mechanism
Abbreviations used in the action plan: VET Institutions - vocational educational institutions; SSO - Sectoral Skills Organizations; HEIs - higher educational institutions; ADB - Asian Development Bank; KFW - German Reconstruction Credit Bank; UNDP - United Nations Development Program; EU - European Union; GIZ - German Society for International Cooperation.
* Note: the donor budget provided for in the action plan may change during the implementation, and accordingly, depending on the need, the current action plan may be revised.

## HEI AP
Sectoral priority 1 |  | Quality and sustainable education and science systems focused on the needs of students, society, and the state
Goal 1.4: |  |  | Personal development and preparation for the labor market of each student by the higher educational institution (HEI) |  |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  | Goal 4. Quality education Goal 8. Decent work and economic growth Goal 9 Industry, innovation, and infrastructure Goal 16 Peace, justice, and strong institutions
Impact indicator 1.4.1: |  |  | Graduates' employment rate |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2020 | 2025 | 2030 |  | https://www.geostat.ge/en/modules/categories/683/Employment-Unemploymehttps: National Survey of HEIs' Graduates
[6 empty] | Indicator | 55% | 65% | 80%
Impact indicator 1.4.2: |  |  | Students' satisfaction rate: (1) international students; (2) local students |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2021 | 2025 | 2030 |  | International and national survey of Eurostudent
[6 empty] | Indicator | (1) 59.5%; (2) 40-45% | (1) 70%; (2) 50-55% | (1) 80%; (2) 60%
Objective 1.4.1: |  |  | Provision of labor market-adapted programs by higher education institutions
Outcome indicator 1.4.1.1: |  |  | Share of programs that provide students with entrepreneurial skills and competencies |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science survey
[6 empty] | Indicator | N/A | 20% | 50% | 80%
Risk: |  |  | Insufficient financial support to higher educational institutions; interest deficiency
Activity |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
1.4.1.1 | Preparation of technical documentation to create a graduate tracking system |  |  | 1.4.1.1(1) | Technical documentation is prepared | The World Bank project Innovatopn, Inclusion, Quality website | Ministry of Education and Science | HEIs | II quarter of 2022 | 90138 |  |  | 90138 | World Bank
1.4.1.2 | Development of a national student survey |  |  | 1.4.1.2(1) | A national students survey system is developed | Students national survey report | Ministry of Education and Science | HEIs | IV quarter of 2024 | Administrative cost
1.4.1.3 | Development of cluster accreditation of educational programs |  |  | 1.4.1.3(1) | Cluster accreditation of educational programs has been developed | Regulating Act of acceditation procedures | NCEQE/Ministry of Education and Science | HEIs | IV quarter of 2024 | Administrative cost
1.4.1.4 | Elaboration of sectoral benchmarks |  |  | 1.4.1.4(1) | Sectoral benchmarks have been elaborated | Sectoral benchmarks document | NCEQE/Ministry of Education and Science | HEIs | IV quarter of 2024 | Administrative cost
1.4.1.5 | Introduction of cybersecurity training courses in higher education institutions |  |  | 1.4.1.5(1) | At least 3 HEIs have introduced the cybersecurity training courses | HEIs websites | Ministry of Education and Science | HEIs | IV quarter of 2023 | Administrative cost
1.4.1.6 | Revising of curricula to strengthen entrepreneurial skills and competencies |  |  | 1.4.1.6(1) | Curricula have been revised | HEIs websites | HEIs/NCEQE/Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
1.4.1.7 | Defining additional regulated professions/specialties following the harmonization of the national qualifications framework with European directives |  |  | 1.4.1.7(1) | At least 6 professions/specialities are adjusted | Quality assurance report | NCEQE/Ministry of Education and Science | Ministry of Internally Displaced Persons from the Occupied Territories, Health, Labour and Social Affairs of Georgia/High Education Institutions | IV quarter of 2024 | Administrative cost
1.4.1.8 | Updating the regulatory framework of higher education and initiating approval by the government to promote the digital transformation of the field |  |  | 1.4.1.8(1) | The regulatory framework for higher education has been updated and initiated for government approval | Ministry of Education and Science Report | Ministry of Education and Science |  | III quarter of 2023 | Administrative cost
1.4.1.9 | Development and initiation of amendments to the "Labor Code" of Georgia to protect the rights of students as employees |  |  | 1.4.1.9(1) | Amendments to the "Labor Code" have been developed and initiated | Legislative amendment project | Ministry of Education and Science | HEIs | IV quarter of 2024 | Administrative cost
1.4.1.10 | Elaborating of a policy document on the recognition of non-formal education |  |  | 1.4.1.10 (1) | The document of nonformal education recognition has been elaborated | Respective regulatory framework | Ministry of Education and Science/ NCEQE |  | IV quarter of 2024 | Administrative cost
1.4.1.11 | Development of the higher education policy document of the third mission in cooperation with higher educational institutions |  |  | 1.4.1.11(1) | The policy document of the third mission in the field of higher education has been developed | Webpage of respective Erazmus+ project | Ministry of Education and Science | HEIs | IV quarter of 2023 | Administrative cost
1.4.1.12 | Creation of excellence centers of the third mission |  |  | 1.4.1.12(1) | At least 5 execellence centers of the third mission have been created | Excellence Centers Reports | HEIs/Ministry of Education and Science |  | IV quarter of 2024 | 2347062 |  |  | 2347062 | EU
Objective 1.4.2: |  |  | Promotion of international learning and internationalization for students
Outcome indicator 1.4.2.1: |  |  | Number of joint/dual degree programs |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data; National Center for Education Quality Enhancement data
[6 empty] | Indicator | 10 | 20 | 30 | 40
Outcome indicator 1.4.2.2: |  |  | The share of students participating in programs of the total number of students |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[6 empty] | Indicator | 5% | 7% | 8% | 10%
Risk: |  |  | Lack of financial resources; lack of interest
Activity |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
1.4.2.1 | Supporting higher educatonal institutions to receive intrenational accreditation of educational programs |  |  | 1.4.2.1(1) | At least 3 educational programs have received international accreditation | HEIs websites | Ministry of Education and Science | HEIs | IV quarter of 2024 | 11 000 000 | 11 000 000 | 32 04 02 08
1.4.2.2 | Supporting the creation of dual/joint academic programs with international partners |  |  | 1.4.2.2(1) | At least 3 dual/joint academic programs have been developed together with international partners | Approved dual/joint academic programs | Ministry of Education and Science | HEIs | IV quarter of 2024 | Administrative cost
1.4.2.3 | Implementation of programs promoting the international mobility of students |  |  | 1.4.2.3(1) | Participation in international mobility programs of at least 300 students is funded | Supporting documentation for sponsored students | LEPL Center for International Education/Ministry of Education and Science |  | IV quarter of 2024 | 21300000 | 21300000 | 32 04 04
Objective 1.4.3: |  |  | Promotion of development of structured doctoral programs corresponding to international standards
Outcome indicator1.4.3.1: |  |  | The share of structured doctoral programs |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | National Center for Education Quality Enhancement data
[6 empty] | Indicator | 0 | 20% | 40% | 60%
Outcome indicator 1.4.3.2: |  |  | The number of joint doctoral programs with international partners |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | National Center for Education Quality Enhancement data; Education Management Information System (EMIS) data
[6 empty] | Indicator | 3 | not less than 6 | not less than 8 | not less than 10
Risk: |  |  | Insufficient financial support to higher educational institutions; interest deficiency
Activity |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
1.4.3.1 | Funding of doctoral research scholarships on the basis of competition |  |  | 1.4.3.1(1) | At least 150 Ph.D. students are funded | Shota Rustaveli National Science Foundation Report | LEPL Shota Rustaveli National Science Foundation/Ministry of Education and Science | HEIs | IV quarter of 2024 | 1200000 | 1200000 | 32 05 01 02
1.4.3.2 | Creation of doctoral and internship programs in cooperation with the industry sector |  |  | 1.4.3.2(1) | Doctoral and internship programs have been created in cooperation with the industry sector | NCEQE data | HEIs/Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
1.4.3.3 | Creation of joint doctoral programs with international partners |  |  | 1.4.3.3(1) | At least 6 joint doctoral programs have been created together with international partners | HEIs websites | HEIs/Ministry of Education and Science | LEPL Shota Rustaveli National Science Foundation | IV quarter of 2024 | Administrative cost
Sectoral Priority 2 |  | An equitable, inclusive, and diverse education and science system
Goal 2.4: |  |  | Ensuring equal access and success opportunities for the high-quality inclusive higher education |  |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  | Goal 4. Quality education Goal 8. Decent work and economic growth Goal 9 Industry, innovation, and infrastructure Goal 16 Peace, justice, and strong institutions
Impact indicator 2.4.1: |  |  | The percentage of students of different categories from the total number of students enrolled in higher education institutions (students representing ethnic minorities; people with disabilities; low socio-economic status, and other groups) |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2021 | 2025 | 2030 |  | Education Management Information System (EMIS) data
[6 empty] | Indicator | 7% | 17% | 37%
Impact indicator 2.4.2: |  |  | The percentage of graduates of different categories from the total number of graduates (students representing ethnic minorities; people with disabilities; low socio-economic status, and other groups) |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2021 | 2025 | 2030 |  | Education Management Information System (EMIS) data
[6 empty] | Indicator | N/A | 10% increase | 20% increase
Objective 2.4.1: |  |  | Development of targeted support services for disadvantaged students of higher education institutions
Outcome indicator 2.4.1.1: |  |  | Number of postgraduate students receiving need-based financial support |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Education Management Information System (EMIS) data
[6 empty] | Indicator | 9411 | 10% increase | 15% increase | 20% increase
Outcome indicator2.4.1.2: |  |  | The number of high education institutions with effective student support (academic, financial, social) systems |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | HEIs official websites
[6 empty] | Indicator | 10% of HEIs | 30% of HEIs | 50% of HEIs | 60% of HEIs
Risk: |  |  | Insufficient financial resources
Activity |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
2.4.1.1 | Providing scholarships to successful students |  |  | 2.4.1.1(1) | At least 6,000 students are provided with scholarships | Minister's order | Ministry of Education and Science |  | IV quarter of 2024 | 13500000 | 13500000 | 32 04 02 06
2.4.1.2 | Development of schemes of social support programs for students representing ethnic minorities |  |  | 2.4.1.2(2) | Social support schemes for ethnic minority students have been updated | Ministry of Education and Science Annual Report | Ministry of Education and Science | HEIs | IV quarter of 2024 | Administrative cost
2.4.1.3 | Implementation of a support program for socially vulnerable groups, persons living in the occupied territories |  |  | 2.4.1.3(1) | At least 600 students participate in the support program | Ministry of Education and Science Annual Report | Ministry of Education and Science |  | IV quarter of 2024 | 28375000 | 28375000 | 32 04 02 01 32 04 02 02 32 04 02 03 32 04 02 04
Objective 2.4.2: |  |  | Creating a favorable learning environment for each student in higher educational institutions
Outcome indicator 2.4.2.1: |  |  | Share of students satisfied with the adapted learning environment among the surveyed students |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Students' satisfaction survey
[6 empty] | Indicator | N/A | 30% | 50% | 70%
Outcome indicator 2.4.1.2: |  |  | Learning/teaching resources developed for students with special needs |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | State budget
[6 empty] | Indicator | no targetted program | no targetted program | targetted program is initiated | targetted program is enhanced
Risk: |  |  | Inefficient financing system
2.4.2.1 | Adapting educational programs to meet the needs of students with disabilities |  |  | 2.4.2.1(1) | All HEIs are adapted to meet the needs of students with disabilities | Decisions of the Authorization Council | Ministry of Education and Science/HEIs | Ministry of Internally Displaced Persons from the Occupied Territories, Health, Labour and Social Affairs of Georgia | IV quarter of 2024 | Administrative cost
2.4.2.2 | Creating and providing learning/teaching resources for students with special needs |  |  | 2.4.2.2(1) | Learning/teaching resources are designed and offered to students with special needs | Dedicated learning/teaching resources for students with special needs | Ministry of Education and Science/HEIs |  | IV quarter of 2024 | Administrative cost
2.4.2.3 | Supporting HEIs in developing and implementing gender equality policy documents/mechanisms |  |  | 2.4.2.3(1) | At least 5 HEIs have developed and implemented gender equality policy documents/mechanisms | HEIs websites | Ministry of Education and Science/HEIs |  | IV quarter of 2024 | Administrative cost
2.4.2.4 | Creating support centers for students with disabilities in higher educational institutions |  |  | 2.4.2.4(1) | At least 3 higher educational institutions have created a center for supporting students with disabilities | Support Centers' reports | Ministry of Education and Science/HEIs |  | IV quarter of 2024 | Administrative cost
Sectoral priority 3 |  | System of management and accountability of education and science system
Goal 3.4: |  |  | Ensuring sustainability of higher educational institutions |  |  |  | Linkages with the Sustainable Development Goals (SDG): |  |  |  | Goal 4. Quality education Goal 8. Decent work and economic growth Goal 9 Industry, innovation, and infrastructure Goal 16 Peace, justice, and strong institutions
Impact indicator 3.4.1: |  |  | The amount of higher education funding in the state (education) budget |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2021 | 2025 | 2030 |  | State budget
[6 empty] | Indicator | 120 million GEL | 266 million GEL | 270 million GEL
Impact indicator 3.4.2: |  |  | Improved position in the HEI's international ranking indices |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Final
[6 empty] | Year | 2021 | 2025 | 2030 |  | Websites with published international indices
[6 empty] | Indicator | N/A | 3 | 5
Objective 3.4.1: |  |  | Development of a financing system focused on the sustainability of higher education
Outcome indicator 3.4.1.1: |  |  | A new funding model has been introduced |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science Report
[6 empty] | Indicator | no system | system is developed | system is implemented | system is fully operational
Risk: |  |  | The unpreparedness of higher education institutions to adapt to the new funding model
Activity |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
3.4.1.1 | Developing a new financing model in cooperation with international partners/experts, considering local social and economic factors |  |  | 3.4.1.1(1) | A new funding model has been developed | Funding data of higher educational institutions | Ministry of Education and Science |  | IV quarter of 2024 | 33666958 | 33666958 | 32 08
3.4.1.2 | Development of a new admission system in higher education institution |  |  | 3.4.1.2(1) | A new enrollment system has been developed | National Assessment and Exam Centers report | Ministry of Education and Science/NAEC/NCEQE | HEIs | II quarter of 2024 | Administrative cost
3.4.1.3 | Updating the methodology for determining undergraduate/graduate priority areas |  |  | 3.4.1.3(1) | The methodology for determining bachelor's/master's priority areas has been updated | Ministry of Education and Science Report | Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
3.4.1.4 | Development of educational programs with relevance to regional needs |  |  | 3.4.1.4(1) | At least 5 educational programs adapted to the region have been developed | Respective educational programs | Ministry of Education and Science | HEIs | IV quarter of 2024 | 602.097 |  |  | 602.097 | EU
Objective 3.4.2: |  |  | Development of digital information management system for higher education
Outcome indicator 3.4.2.1: |  |  | Level of data digitization in higher education information management system |  |  |  | Baseline | Target |  |  | Source of verification
[8 empty] | Interim | Interim | Final
[6 empty] | Year | 2021 | 2024 | 2027 | 2030 | State budget/Ministry of Education and Science Report
[6 empty] | Indicator | no system | 20% | 50% | 100%
Risk: |  |  | Insufficient financial support
Activity |  |  |  | Output indicator |  | Source of verification | Responsible agency | Partner Agency | Implementation period | Budget | Source of Financing
[11 empty] | State budget |  | Other |  | Deficit
[11 empty] | Amount | Program code | Amount | Organization
3.4.2.1 | Creation and development of a digital archive to consolidate information about students with active and suspended statuses |  |  | 3.4.2.1(1) | Information about students with active and suspended statuses is available through a special program | Launched program | EMIS/Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
3.4.2.2 | Creation of automated software (Uni-Grants) for grant and program funding calculation |  |  | 3.4.2.2(1) | For the Uni-Grants system, functions for calculating the funding of state master's grants and state programs have been added | Improved Uni-Grants System | EMIS/Ministry of Education and Science | HEIs | IV quarter of 2024 | Administrative cost
3.4.2.3 | Creating an electronic higher education quality management system |  |  | 3.4.2.3(1) | An electronic system of quality management of higher education has been created | Digital system | NCEQE/EMIS/Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
Abbreviations used in the Action Plan: EMIS - Education Management Information System; HEIs - higher educational institutions; ShRESF - Shoota Rustaveli National Scientific Foundation; NCEQE - National Center for Education Quality Enhancement; NAEC - National Assessment and Examination Center; EU - European Union.
* Note: the donor budget provided for in the action plan may change during the implementation, and accordingly, depending on the need, the current action plan may be revised.

## STI AP
Sectoral priority 1 |  | Quality and sustainable education and science systems focused on the needs of students, society, and the state
Goal 1.5: |  |  | Development of a knowledge-based society and an economy-oriented science, research, technology, and innovation system | [6 empty] | #REF! |  |  |  |  | #REF!
Impact indicator 1.5.1: |  |  | Share of research and development cost in the total GDP |  |  |  |  | Baseline |  | Target |  |  |  |  | Source of verification
[10 empty] | Interim |  | Final
[6 empty] | Year |  | 2021 |  | 2025 |  | 2030 |  |  | State budget
[6 empty] | Indicator |  | 0,32% |  | 1,2 % |  | 2,5%
Imact indicator 1.5.2 |  |  | European Union's financial contribution (in the "Horizon Europe" framework); the number of projects, and funding |  |  |  |  | Baseline |  | Target |  |  |  |  | Source of verification
[10 empty] | Interim |  | Final
[6 empty] | Year |  | 2021 |  | 2025 |  | 2030 |  |  | Program Horizon (information about Georgia)
[6 empty] | Indicator |  | 56 Projects, 8.23 million Euro |  | 70 projects, 10 million Euro |  | 90 projects, 14 million Euro
Impact indicator 1.5.3: |  |  | Technology transfer rate (commercialization of technologies) |  |  |  |  | Baseline |  | Target |  |  |  |  | Source of verification
[10 empty] | Interim |  | Final
[6 empty] | Year |  | 2021 |  | 2025 |  | 2030 |  |  | Georgia's Innovation & Technology Agency data
[6 empty] | Indicator |  | 0 |  | 5 technological projects are commercialized |  | 23 technological projects are commercialized
Objective 1.5.1: |  |  | Support of researchers in the implementation of research and innovative activities in compliance with international standards
Outcome indicator 1.5.1.1: |  |  | The volume of state-supported funding for novice researchers | [5 empty] | Baseline |  |  | Target |  |  | Source of verification
[12 empty] | Interim | Interim | Final
[6 empty] | Year |  |  | 2019 |  |  | 2024 | 2027 | 2030 | State budget
[6 empty] | Indicator |  |  | 11.7% |  |  | 20% | 30% | 50%
Outcome impact indicator 1.5.1.2: |  |  | Research productivity by citation index/ Citation Index | [5 empty] | Baseline |  |  | Target |  |  | Source of verification
[12 empty] | Interim | Interim | Final
[6 empty] | Year |  |  | 2021 |  |  | 2024 | 2027 | 2030 | Scimago data
[6 empty] | Indicator |  |  | The number of cited documents is about 21,000 |  |  | 20 % increase | 30 % increase | 50% increase
Outcome impact indicator 1.5.1.3: |  |  | The number of innovative "startups" that have received grants from state co-financing schemes | [5 empty] | Baseline |  |  | Target |  |  | Source of verification
[12 empty] | Interim | Interim | Final
[6 empty] | Year |  |  | 2021 |  |  | 2024 | 2027 | 2030 | Georgia's Innovation & Technology Agency data
[6 empty] | Indicator |  |  | 159 |  |  | 279 startups are financed | 399 startups are financed | 519 startups are financed
Risk: |  |  | Lack of financial resources; Lack of interest from researchers
#REF! |  |  |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! |  | #REF! |  | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
1.5.1.1 | Development of a new quality-oriented recruitment system |  |  | 1.5.1.1.(1) | A new quality-oriented recruitment system has been developed |  | Ministry of Education and Science Annual Report | Ministry of Education and Science/ShRNSF | HEIs/LEPL Research Institutes | IV quarter of 2023 | Administrative cost
1.5.1.2 | Creating a career development system and sustainable/transparent funding schemes |  |  | 1.5.1.2 (1) | Sustainable and effective funding schemes for novice researchers have been developed |  | Contests and awards published on the websites of ShRNSF, HEIs, and research institutes; Annual Report of the Ministry of Education and Science | ShRNSF/Ministry of Education and Science | HEIs/LEPL Research Institutes | IV quarter of 2023 | 2119000 | 2119000 | 32 05 01 32 05 02 32 05 04
|  |  |  | 1.5.1.1.2 (2) | Intersectoral, interdisciplinary, and international mobility scholarships, research trips, and grants for master's, doctoral and postdoctoral students have been introduced
1.5.1.3 | Development and submission of legislative proposals for the creation of a national system for awarding the researcher emeritus title |  |  | 1.5.1.1.3(1) | Amendments to the Law of Georgia "On Higher Education" have been developed and initiated |  | Legislative Herald of Georgia | Ministry of Education and Science | HEIs/LEPL Research Institutes | IV quarter of 2024 | Administrative cost
1.5.1.4 | Preparation of relevant bases for the creation of research and innovation cluster centers |  |  | 1.5.1.4(1) | The basis for the creation of cluster centers has been prepared (technical sciences, technologies, engineering, mathematics, the study of the Georgian language, humanitarian and social sciences) |  | Respective legislative Acts | Ministry of Education and Science/ShRNSF |  | II quarter of 2023 | 10000000 | 10000000 | 32 05 04
1.5.1.5 | Participation of researchers in international projects and programs |  |  | 1.5.1.5(1) | At least 100 researchers participated in international projects and programs |  | Grant agreements | Ministry of Education and Science/ShRNSF | HEIs/LEPL Research Institutes | IV quarter of 2024 | 5306268 |  |  | 5306268 | EU
1.5.1.6 | Implementation of financial levers to improve scientific bibliometric data of Georgian researchers |  |  | 1.5.1.6(1) | Scientific bibliometric data of Georgian researchers has been improved (publications, citations, H index) |  | Sub-programme of the Scientific Research Promotion Program "Support for Open Science" | ShRNSF/Ministry of Education and Science | Research Institutes | IV quarter of 2023 | 1400000 | 1400000 | 32 05 04 06
1.5.1.7 | Improvement of technology transfer system at the national and global scale |  |  | 1.5.1.7(1) | The technology transfer support system has been improved |  | Respective legislative Acts | Georgia's Innovation and Technology Agency | Ministry of Education and Science/HEIs/Research Institutes | IV quarter of 2023 | Administrative cost
1.5.1.8 | Development of a methodology for measuring the commercial potential of research ideas |  |  | 1.5.1.8(1) | A methodology for measuring the commercial potential of research ideas has been developed |  | Commercial potential measurement methodology and reports | Georgia's Innovation and Technology Agency | HEIs/LEPL Research Institutes | IV quarter of 2023 | Administrative cost
Objective 1.5.2: |  |  | Ensuring academic and research integrity in teaching and research
Outcome indicator 1.5.2.1: |  |  | The share of HEIs that have updated effective academic integrity and anti-plagiarism policies | [7 empty] | Baseline | Target |  |  | Source of verification
[12 empty] | Interim | Interim | Final
[8 empty] | Year |  |  | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science Annual Report
[8 empty] | Indicator |  |  | N/A | 10% | 30% | 50%
Risk: |  |  | Lack of financial resources
#REF! |  |  |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! |  | #REF! |  | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF!
1.5.2.1 | Training of higher education institutions and scientific personnel in academic and research integrity |  |  | 1.5.2.1.(1) | Teachers and administrative staff of at least 50% of HEIs are trained |  | ტრენინგზე დაწრების ფურცელი | Ministry of Education and Science | HEIs | IV quarter of 2023 | Administrative cost
1.5.2.2 | The persons responsible for the assessment of academic and research integrity are defined in the Higher Education Institutions |  |  | 1.5.2.2(1) | Persons responsible for the assessment of academic and research integrity have been defined in all HEIs |  | HEIs reports | HEIs/Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
1.5.2.3 | Procuring licenses to verify academic and research integrity |  |  | 1.5.2.3(1) | At least 2 licenses have been purchased |  | Procurement documentations | Ministry of Education and Science | HEIs | IV quarter of 2024 | Administrative cost
Sectoral priority 2 |  |  | #REF!
Goal 2.5: |  |  | Supporting public engagement in the creation of inclusive and diverse science, research, technology, and innovation | [5 empty] | #REF! |  |  |  | #REF!
Impact indicator 2.5.1: |  |  | The number of participants in local and international competitions in research, technology, and innovation | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Final
[8 empty] | Year | 2021 | 2025 | 2030 |  | Ministry of Education and Science/Georgia's Innovation & Technology Agency (GITA) data
[8 empty] | Indicator | N/A | 40% | 60%
Objective 2.5.1: |  |  | Enhancing interest in research, technology, science, and innovation from an early stage of education
Outcome indicator 2.5.1.1: |  |  | The number of children and youth involved in the school communication programs with universities and/or research institutes | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Interim | Final
[8 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science report
[8 empty] | Indicator | 1000 | 5000 | 10000 | 15000
Risk: |  |  | Lack of administrative support in municipalities and lack of communication between higher education institutions and schools
#REF! |  |  |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! |  | #REF! |  | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF!
2.5.1.1 | Integrating the research approach into the learning/teaching process at the stage of school education (from STEM to STEAM) |  |  | 2.5.1.1(1) | Research approaches are integrated into school education (from STEM to STEAM) |  | Ministry of Education and Science Annual Report, NCEQE Data on Accredited Programs | Ministry of Education and Science/ShRNSF/ NCEQE | HEIs | IV quarter of 2023 | Administrative cost
2.5.1.2 | Development of state school communication programs in STEM/STEAM fields |  |  | 2.5.1.2(1) | Communication program has been developed |  | Ministry of Education and Science Report | Ministry of Education and Science | HEIs | IV quarter of 2023 | Administrative cost
2.5.1.3 | Introduction of optional training courses focused on the development of initial skills needed for research and innovation at the final stage of the bachelor's program |  |  | 2.5.1.3(1) | Relevant training courses are integrated into at least 5 curricula |  | NCEQE report | Ministry of Education and Science/NCEQE | HEIs | IV quarter of 2024 | Administrative cost
2.5.1.4 | Implementation of targeted programs and projects to increase public interest in science, technology, research, and innovation |  |  | 2.5.1.4(1) | 10 targeted programs and scientific festivals have been held |  | Ministry of Education and Science Annual Report | ShRNSF/Ministry of Education and Science | HEIs/LEPL Research Institutes | IV quarter of 2024 | 1130000 | 1130000 | 32 05 01 02; 32 05 05
Objective 2.5.2: |  |  | Supporting women's involvement in science, research, technology, and innovation
Outcome indicator 2.5.2.1: |  |  | Percentage of women in scientific councils and high academic staff | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Interim | Final
[8 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministry of Education and Science Report
[8 empty] | Indicator | N/A | 10% | 20% | 30%
Outcome indicator 2.5.1.2: |  |  | Percentage of female graduates in STEM fields | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Interim | Final
[8 empty] | Year | 2021 | 2024 | 2027 | 2030 | Ministy of Education and Science data
[8 empty] | Indicator | 41% | not less than 45 % | not less than 50 % | not less than 55 %
Risk: |  |  | Lack of stakeholders' interest, low level of readiness
#REF! |  |  |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! |  | #REF! |  | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF!
2.5.2.1 | Developing a resource allocation mechanism for research and innovation, considering the gender equality principle |  |  | 2.5.2.1(1) | The distribution of resources for research and innovation is gender balanced |  | National data on women's engagement/participation in resource allocation for Research & Innovation | Ministry of Education and Science | HEIs/LEPL Research Institutes | IV quarter of 2024 | Administrative cost
2.5.2.2 | Creating a digital platform for career planning and empowerment of girls/women in STEM fields |  |  | 2.5.2.2(1) | A digital platform has been created to find best practice cases and information on gender issues within the STEM cluster |  | Ministry of Education and Science Annual Report; Digital platform | ShRNSF/Ministry of Education and Science | HEIs/LEPL Research Institutes | IV quarter of 2024 | 1100000 | 1100000 | 32 05 01 02
|  |  |  | 2.5.2.2(2) | The number of girls and women winning STEM competitions has increased by 20%
Sectoral priority 3 |  |  | #REF!
Goal 3.5: |  |  | Improving the efficiency of research, science, technology, and innovation systems |  |  |  |  | #REF! |  |  |  |  | #REF!
Impact indicator 3.5.1: |  |  | Success index science, research, technology & innovation funded by Horizon | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Final
[8 empty] | Year | 2021 | 2025 | 2030 |  | Program Horizon (Information about Georgia)
[8 empty] | Indicator | 8 winning projects | 25% increase | 50% increase
Impact indicator 3.5.2: |  |  | Indicator of implementation of PSF recommendations | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Final
[8 empty] | Year | 2021 | 2025 | 2030 |  | Report on PSF recommendations implementation
[8 empty] | Indicator | 7 | 14 | 23
bjective 3.5.1: |  |  | Development of a long-term, result-oriented, and targeted funding system for science, research, innovation, and technology
Outcome indicator 3.5.1.1: |  |  | Funding volume for long-term targeted research | [5 empty] | Baseline | Target |  |  | Source of verification
[10 empty] | Interim | Interim | Final
[8 empty] | Year | 2021 | 2024 | 2027 | 2030 | State budget
[8 empty] | Indicator | 30,7 million GEL | 35 million GEL | 38 million GEL | 41 million GEL
Risk: |  |  | Lack of financial resources, global challenges
#REF! |  |  |  | #REF! |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[12 empty] | #REF! |  | #REF! |  | #REF!
[12 empty] | #REF! | #REF! | #REF! | #REF!
3.5.1.1 | Development of a new model of the competitive (contest) system of funding at the national and institutional levels |  |  | 3.5.1.1(1) | A model of a competitive (contest-based) financing system has been developed |  | Share of basic and competition-based financing from the state budget | ShRNSF/Ministry of Education and Science |  | IV quarter of 2023 | 3786046 | 3786046 | 32 05 01
3.5.1.2 | Scientific research funding |  |  | 3.5.1.2(1) | The number of funded research has increased by 10% |  | HEIs internal financing schemes | Ministry of Education and Science | HEIs | I quarter of 2024 | 47000000 | 47000000 | 32 05 04
3.5.1.3 | Financing grant competitions |  |  | 3.5.1.3(1) | The number of financed grant competitions has increased by 10% |  | State budget and advertised competitions | ShRNSF/Ministry of Education and Science |  | IV quarter of 2024 | 3786046 | 3786046 | 32 05 01
3.5.1.4 | Developing a model of external financing of higher education institutions in cooperation with the industrial sector |  |  | 3.5.1.4(1) | An external financing model has been developed |  | ShRNSF monitoring report/State budget | ShRNSF/Ministry of Education and Science | Ministry of Economy and Sustainable Development/Georgia's Innovation & Technology Agency/HEIs/ Research Institutes | IV quarter of 2023 | ადმინისტრაციული ხარჯი
3.5.1.5 | Expanding the network of university grant offices and providing research & innovation support services |  |  | 3.5.1.5(1) | Training programs for providing research & innovation support services have been developed for research managers and professional staff |  | Training materials; Lists of participants | Ministry of Education and Science | HEIs/LEPL Research Institutes | IV quarter of 2022 | 250000 | 250000 | 32 05 01 03 |  | EU
3.5.1.6 | Implementation of science management schools' training programs for target groups |  |  | 3.5.1.6(1) | Training programs of the Science Management School have been introduced |  | Ministry of Education and Science Annual Report | Ministry of Education and Science | HEIs | IV quarter 2022 | 150000 | 150000 | 32 04 02 08
3.5.1.7 | Implementation of PSF (Policy Support Facility) recommendations |  |  | 3.5.1.7(1) | At least 10 recommendations have been implemented |  | Ministry of Education and Science Report | Ministry of Education and Science |  | IV quarter of 2024 | Administrative cost
3.5.1.8 | Conclusion of university-industrial sector cooperation agreements |  |  | 3.5.1.8(1) | At least 3 agreements have been concluded between the university and the industrial sector |  | Agreements signed between industry sectors and universities | Ministry of Education and Science | HEIs/Ministry of Economy and Sustainable Development/Georgia's Innovation & Technology Agency | IV quarter of 2023 | Administrative cost
3.5.1.9 | Facilitating the development of innovation ecosystem hubs that provide services relevant to regional needs and capacities |  |  | 3.5.1.9(1) | 200 training sessions have been conducted in technoparks and digital production laboratories in compliance with regional needs and capacities |  | Training materials and attendance sheets for trained personnel | Ministry of Economy and Sustainable Development | Ministry of Education and Science/Ministry of Regional Development and Infrastructure/Georgia's Innovation & Technology Agency/HEIs | IV quarter of 2022 | Administrative cost
3.5.1.10 | Creation of scientific laboratory(s) of international standards |  |  | 3.5.1.10(1) | Scientific laboratory/s of international standards of common use have been established |  | Respective legislative acts | Ministry of Education and Science/ShRNSF |  | IV quarter of 2023 | 1500000 | 1500000 | 32 05 04 06
3.5.1.11 | Creation of an open database of Georgian scientists to implement an "open science" policy |  |  | 3.5.1.11(1) | An open database of research activities of Georgian scientists has been developed |  | National Research Digital Platform | Ministry of Education and Science/ShRNSF |  | IV quarter of 2022 | 1396500 | 1396500 | 32 05 04 06
3.5.1.12 | Integrating the national research digital platform into European networks |  |  | 3.5.1.12(2) | The national research digital platform is integrated into European networks |  | Ministry of Education and Science Annual Report | Ministry of Education and Science | HEIs/LEPL Research Institutes | IV quarter of 2023 | Administrative cost
3.5.1.13 | Elaborating a legal basis for the creation of a technology transfer support center |  |  | 3.5.1.13(1) | Respective legislation/by-laws are elaborated |  | Relevant legislation/by-laws | Ministry of Education and Science | Ministry of Economy and Sustainable Development/Georgia's Innovation & Technology Agency | IV quarter of 2023 | 170000 | 170000 | 32 05 04 06
3.5.1.14 | Creating accelerators and incubators to develop an innovative ecosystem |  |  | 3.5.1.14(1) | A total of 10 accelerators and incubators have been created |  | Procurement documents | Ministry of Economy and Sustainable Development/Georgia's Innovation & Technology Agency | Ministry of Education and Science | IV quarter of 2023 | 9535000 | 9535000 | 24 08 02
Abbreviations used in the Action Plan: ShRESF - Shoota Rustaveli National Scientific Foundation; HEIs - higher educational institutions; NCEQE - National Center for Education Quality Enhancement; NAEC - National Assessment and Examination Center; EU - European Union.
* Note: the donor budget provided for in the action plan may change during the implementation, and accordingly, depending on the need, the current action plan may be revised.