## PS
Objective | Activity | Expected output | Responsible Entity | Partner entity | Implementation Period | Estimated budget | Funding Source
Specific goal: increase access to high quality preschool education and ensure readiness of school age children for school
1. Strategic objective: Promote the development of high quality, inclusive and equally accessible pre-school education system for the pre-school education institutions.
1. Strategic objective: Promote the development of high quality, inclusive and equally accessible pre-school education system for the pre-school education institutions. | 1.1 To ensure the improvement of the standard and the compliancy of the document with the National Curriculum, review the results of monitoring on implementation of the state standard for early and preschool education, including school readiness standard, and prepare the respective recommendations with the engagement of the stakeholders. | The recommendations obtained as a result of monitoring are reviewed with the engagement of the stakeholders. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 14500 | The state budget;
| 1.2 Identification of methodological and educational resources developed by various governmental or non-governmental organizations existing in the country, determining their compliance with the standards and preparation of list. | Identified resources will be placed on the portal of electronic library http://el.ge/ | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | Administrative resource | The state budget; donors' projects
| 1.3 Preparation of methodological resources and educational materials for facilitating the implementation of the state standard for early and preschool education, including the school readiness standard. | The methodological textbook and collection of activities for a caregiver-pedagogue working in the age group 2-5 is prepared; The methodological textbook for a caregiver-pedagogue working in the mixed age groups. | The Ministry of Education, Science, Culture and Sport of Georgia | UNICEF | 2019 | 75000 | The state budget; donors' projects
| 1.4 Development of programs based on inclusive and civil education principles and preparation of the list of respective educational resources. | Main and supporting education materials for the program of school readiness were determined. | The Ministry of Education, Science, Culture and Sport of Georgia | UNICEF/ Save the Children | 2019 | Administrative resource | The state budget; donors' projects
| 1.5 Pilot implementation of the state educational standards in the one kindergarten of Tbilisi. | The pilot implementation of the standard was conducted in the groups of school readiness of two prechsool care and education institutions. The training module of school readiness program is updated and the recommended plan of supervision process is developed. | LEPL National Center for Teacher Professional Development; Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 40000 | The state budget;
| 1.6 Development of the regulating document for inclusive early and preschool education. | The interdepartmental regulating document for early and preschool inclusive education was developed. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 |  | The state budget (administrative resource); donors projects
| 1.7 Facilitating awareness of parents about a preschool education. | The guide "Tips and recommendations for parents of early and preschool age children" is available. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 5000 | The state budget; donors' projects
2.Support and implement the training / retraining programs for preschool education personnel | 2.1 Establishment of the professional development system for a caregiver-pedagogue and a caregiver. | The respective action plan is developed; The Higher Education Sector Benchmark for Early (Pre-school) Education" is developed (prepared for approval). | LEPL National Center for Teacher Professional Development; LEPL National Center for Educational Quality Enhancement |  | 2019 | Administrative resource | The state budget; donors' projects
| 2.2 Support capacity development of personnel for the system of preschool education | 529 educational supervisors/coordinators of preschool institutions were retrained by means of the "Training Module for Professional Development of Caregiver-Pedagogues" (2018-2019); the "Training Programme for the Trainers of the Module for Professional Development of Caregiver-Pedagogues" is developed. Up to 40 representatives of the organizations defined by the "Training Module for Professional Development of Caregiver-Pedagogues" are retrained as trainers. The list of the organizations and trainers is public and availeble by municipalities. | The Ministry of Education, Science, Culture and Sport of Georgia | LEPL National Center for Teacher Professional Development | 2019 | 90652 | The state budget; donors' projects
| 2.3 Developing the database of educational personnel of preschool institutions for appointment on the position of caregiver-pedagogue. | The data base is created; The data processing is going on. | The Ministry of Education, Science, Culture and Sport of Georgia | LEPL National Center for Teacher Professional Development | 2019 | Administrative resource | The state budget
| 2.4 Retraining the employees of the educational resource centers. | The training module for the personnel of educational training centers was developed; the number of retrained persons. | The Ministry of Education, Science, Culture and Sport of Georgia | LEPL National Center for Teacher Professional Development | 2019 | 61000 | The state budget
3. Development and implementation of preschool education quality monitoring and evaluation system | 3.1 Development of the monitoring instrument and pilot implementation in 3 institutions of preschool care. | The monitoring instrument is implemented in 3 institutions. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 14500 | The state budget;
| 3.2 Monitoring of intitutios of preshcool education. | The intermediate results of monitoring commenced in 15 institutions, are reflected in the report. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019

## GE
Objective | Activity | Expected output | Responsible Entity | Partner entity | Implementation Period | Estimated budget | Funding Source
Specific Goal: Ensure access to high quality general education and educational outcomes relevant to national and international standards for preparing students for future life
1.Strategic Objective: Providing equal, universal access to high quality general education
1. Increase geographical access to quality education | 1.1 Providing transportation of students of Tbilisi and Adjara region. | Within the framework of the program of providing transportation to the students of public schools, up to 14000 students of around 200 public schools in Tbilisi and Adjara region have an access to the free of charge transport. | The Ministry of Education, Science, Culture and Sport of Georgia | Local self-government authority; | 2019 | 7085839.89 | The state budget
| 1.2 Providing access to education for the students from the occupied territories | Up to 840 teachers and 260 administrations on the occupied territories of Georgia are provided with financial aid for the integration of students living on these territories, into the educational sphere of Georgia, and for facilitating availability of higher educations for enrollees. | The Ministry of Education, Science, Culture and Sport LEPL National Examination and Assessment Center | The Ministry of Education and Culture of Autonomous Republic of Abkhazia Administration of South Ossetia | 2019 | 4226000 | The state budget
| 1.3 Financing boarding schools in high-mountainous areas. | Up to 30 beneficiaries of the subprogram are provided with boarding service in the boarding schools of the villages Barisakho, Magaroskari and Shatili in the Dusheti municipality. | The Ministry of Education, Science, Culture and Sport of Georgia | Local self-government authority 1,000,000 | 2019 | 125893 | The state budget
| 1.4. Ensuring access to general education for various vulnerable groups. | Minors iving in penitentiary institutions and migration centers are provided with general education service. For minors seeking refuge, or refugees and minors with humanitarian status, the Georgian language courses are available. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 258654 | The state budget
2. Increase coverage of inclusive education and implementation of needs oriented programs | 2.1 Ensuring the appropriate educational environment for students with special educational needs. | The methodology of teaching the students with special educational needs is refined; The alternative and expanded curriculum is implemented; Teachers improved their qualification in the methodology of teaching the students with special educational needs; retraining of special teachers is underway. | LEPL National Center for Teacher Professional Development; The Ministry of Education, Science, Culture and Sport of Georgia. |  | 2019 | Within the scope of inclusive education program - 140000; TPDC- 600000 | The state budget
| 2.2 Providing school students with free of charge textbooks and other educational resources. | Students of 1-12 grades in the public schools of Georgia are provided with free of charge textbooks; Blind and low vision students are provided with textbooks with Braille alphabet and relief pictures. | The Ministry of Education, Science, Culture and Sport of Georgia; LEPL Educational and Scientific Infrastructure Development Agency |  | 2019 | 21320135 | The state budget
| 2.3 Development of multidisciplinary teams | For the purpose of identifying the needs of child, the instrument evaluating the development of child in the age from 6 months to 6 years is translated, the study is performed to fit the evaluation test to the Georgian norms; | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 30000 | The state budget
| 2.4 Improving the infrastructure for increasing access of the students with special educational needs to the education. | Construction of 5 fully adapted schools is completed, construction of 12 schools is ongoing, construction of additional 4 schools commences, rehabilitation works of 140 schools are completed, according to the requirements for arranging an environment for the students with special educational needs (considering the structural situation of buildings). | LEPL Educational and Scientific Infrastructure Development Agency |  | 2019 | 95541697 | The state budget
| 2.5 Continuous implementation of special educational service (bridge or transit programs) for integration and reintegration of minors left outside schools or having a high risk of leaving outside. | The updated program ensures continuous service for all (120-150) beneficiaries of the 6 day centers of the LEPL Social Service Agency. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 150000 | The state budget
3. Multilateral development of education supporting models | 3.1 Expanding remote teaching of Georgian language for Georgian children living abroad. | Teachers are retrained accordingly; the number of students involved in the program increased by 25%. | LEPL Educational and Scientific Infrastructure Development Agency; The Ministry of Education, Science, Culture and Sport of Georgia | LEPL Education Management Information System, Microsoft Georgia, MCC | 2019 | 220000 | The state budget
2. Strategic Objective: Improve the quality of education to increase the possibilities of transition to the next level of learning, to develop vital skills in the students and achieve better academic results
1.Modernization of National Curriculum | 1.1 Implementation of the curriculum for elementary stage in the non-Georgian language schools/sectors | certified textbooks are translated into Azerbaijani/Armenian/Russian languages. | LEPL Educational and Scientific Infrastructure Development Agency | LEPL Education Management Information System | 2019 | 2357138 | The state budget
| 1.2 Implementation of the National Curriculum on the basic stage | a) Implementation of the new National Curriculum is launched b). All students of VII grade of basic stage in Georgian language public schools are provided with the certified updated textbooks. | LEPL Educational and Scientific Infrastructure Development Agency; LEPL Education Management Information System |  | 2019 | 3,287,095 1, 220. 000 (EMIS budget) | The state budget
| 1.3 Implementation of alternative curriculum for the students with severe, deep and multiple disorders | Teachers of resource schools (for the students with severe and deep intelectual disorders) are retrained for implementation of the alternative curriculum. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 15000 | The state budget
| 1.4 Development of teaching the following disciplines: human rights, equality, global citizenship, media literacy, digital citizenship and sustainable development, basic entrepreneurial skills. | The number of activities/participants of trainings and other forms of professional development, in relation to human rights, equality, global citizenship, entrepreneurship, media literacy, digital citizenship and sustainable development | LEPL National Center for Teacher Professional Development | HEIs, associations, non-governmental organizations | 2019 | 73000 | The state budget
2. Improve and diversify educational resources at all levels of general education | 2.1 Certification of school textbooks of elementary and basic stages of general education, in accordance with the new National Curriculum. | The procedures of certification for some textbooks of I-VII grades and all textbooks of VIII grade of the basic stage are ongoing. | Ministry of Education, Science, Culture and Sport of Georgia, LEPL Education Management Information System |  | 2019 | 3980000 | The state budget
| 2.2 Development of electronic educational resources for students, development of EL.GE electronic portal | Educational electronic resources for the students of elementary stage are developed, which ensure the implementation of game methods of teaching. EL.GE electronic portal is established, where various Georgian electronic resources are available. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Education Management Information System |  | 2019 | 221610 | The state budget
| 2.3 Facilitating in teaching human rights, equality, global citizenship, sustainable development, entrepreneurship and other important topics | Gobal citizenship and goals of sustainable development, teaching of entrepreneurship are reflected in the educational resources for teachers. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Teacher Professional Development |  | 2019 | Administrative resource | The state budget
| 2.4 Development of school infrastructure - equipment of schools with technologies, school labs, development of libraries. | Classrooms of 166 pilot schools are equipped with digital means (projectors, laptop charger boxes and portable computers), and public schools are provided with computers according to the request. | LEPL Educational and Scientific Infrastructure Development Agency | LEPL Education Management Information System; Ministry of Education, Science, Culture and Sport of Georgia; MCC | 2019 | 6919539 | The state budget
3. Improve learning and teaching quality | 3.1 Improvement of the scheme of professional development and career advancement of teachers, in terms of compliance of teaching quality. | The subject-matter and content of the resources facilitating the implementation of the scheme are defined and redeveloped; the full documentation and statistical data is prepared, needed for granting statuses envisaged by the schedule; the compliance of granted statuses of teachers submitted for the status change, is defined; the pre-service teacher program is activated. | LEPL Educational and Scientific Infrastructure Development Agency; Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | Administrative resource | The state budget
| 3.2 Development of partnership between schools. | For the purpose of sharing the partnership experience, working groups are established; the number of joint projects and activities is increased. | Schools; Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Teacher Professional Development |  | 2019 | 61165.4 | The state budget
| 3.3 Comprehensive development of competitions and Olympiads. | Competitions and Olympiads are diversiffied (5 topical competition, national Olympliads in 13 subjects, international Olympliads in 5 subjects). | Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 600686 | The state budget
| 3.4 Facilitating extracurricular art educatiion | 12,000 students and 650 teachers of the public schools of Tbilisi will participate in the educational tours in Museums; 9,500 students and 290 teachers of the public schools will attend theatrical plays. 8,000 students and 200 teachers of the public schools will attend musical concerts. | Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 149510 | The state budget
| 3.5 Implementation of the "New School Model" in public schools. | The school curriculum based on constructivist educational principles is implemented in 165 public schools, as well as effective practice of school management, digital technologies in the process of learning and teaching, the evaluation system of facilitating advance and development. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Educational and Scientific Infrastructure Development Agency; LEPL Education Management Information System; LEPL Educational and Scientific Infrastructure Development Agency |  | 2019 | 23981233 | The state budget
4.Improve learning and teaching quality using national and international assessments | 4.1 Establishment of effective mechanism with the purpose to reflect the results of international evaluation in the process of decision-making. | The draft version of the mechanism is reviewed and agreed between the stakeholders. | LEPL National Assessment and Examination Center; Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 10000 | The state budget
| 4.2 Establishment of mechanisms of considering the results of national evaluations in the process of development of educational program. | The draft version of the mechanism is reviewed and agreed between the stakeholders. | LEPL National Assessment and Examination Center; Ministry of Education, Science, Culture and Sport of Georgia |  | 2019
3. Strategic Objective: improve educational environment
1. Bring the infrastructure of educational institutions into compliance with modern educational standards | 1.1 Arrangement/rehabilitation of indoor and outdoor sports fields for the purpose of promotion of healthy lifestyle. | In 2019, the arrangement/rehabilitation of sports halls of 15 public schools will be carried out and the arrangement/rehabilitation of sports fields of 23 public schools. | LEPL Educational and Scientific Infrastructure Development Agency; The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 |  | The state budget (from the program of development of infrastructure of general education institutions).
| 1.2 Providing schools with ICT technologies and high-speed internet. | Classrooms of I-IV grades in 165 public schools are equipped with protectors, notebooks for teachers. Computer laboratories are updated, mobile cabinets for storing/charging laptops are introduced, a wireless Wi-Fi network is arranged in 386 schools. In all public schools throughout Georgia, the high-speed internet connection is established. | LEPL Education Management Information System, LEPL Educational and Scientific Infrastructure Development Agency , |  | 2019 | 18948695 | The state budget
2. Create safe, healthy, caring and friendly learning environment tailored to each student's interest | 2.1 Promotion of intercultural education in schools, development of the culture of diversity and tolerancy. | The issues of diversity and tolerancy are reflected in the respective training modules for improving intercultural competencies; the guidelines are available for teachers. | LEPL National Center for Teacher Professional Development, Ministry of Education, Science, Culture and Sport of Georgia | HEIs, associations | 2019 | Administrative resource | The state budget
| 2.2 Expanding the availability of the service of LEPL - Mandaturi Service of Educational Institution. | The LEPL - Mandaturi Service of Educational Institution is introduced into 130 new public schools. | LEPL Mandaturi Service of Educational Institution |  | 2019 | 810000 | The state budget
| 2.3 Opening 2 centers of psychological and social service of the LEPL - Mandaturi Service of Educational Institution in Akhaltsikhe and Zugdidi. | In Akhaltsikhe and Zugdidi, 2 new centers of psychological and social service of the LEPL - Mandaturi Service of Educational Institution are functioning; the number of beneficiaries of the center. | LEPL Mandaturi Service of Educational Institution |  | 2019 | 60000 | The state budget
| 2.4 Improvement of school environment, prevention of violence/bullying/drag use/reduction and minimization of risks and promotion of healthy lifestyle. | The program of bullying prevention was implemented; the program of drag use prevention. | LEPL Mandaturi Service of Educational Institution |  | 2019 | Administrative resource | The state budget
[6 empty] | 73000 | Grant (UNICEF)
| 2.5 Strengthening the LEPL - Mandaturi Service of Educational Institutution | Unified approaches and standards for providing a psychological and social services are developed and implemented; the portal www.befriend.mes.gov.ge is modified to the final condition and beneficiaries can receive an online consultation; 350 acting "mandaturis" are retrained according to the updated teaching module; in those schools of Georgia, where mandaturi service is not presented, the authorized persons are retrained by means of respective training module. | LEPL Mandaturi Service of Educational Institution |  | 2019 | Administrative resource | The state budget
| 2.6 Equipping the authorized persons (responsible for security) with metal detectors. | The authorized persons in public schools of Georgia are equipped with metal detectors. | LEPL Mandaturi Service of Educational Institution |  | 2019 | 120450 | The state budget
4. Strategic Objective: Increase motivation and effectiveness of school administration and teachers
1. Promotion of the profession of teacher. | 1.1. Stimulating the beginner teachers with the purpose of emininating deficit of teachers in the non-Georgian language schools and schools in mountanous regions with low number of students. | The following programs are implemented: "Teach for Georgia"; "Professional support for non-Georgian language school"; "Remote teaching", which is aimed at overcoming the deficit of teachers; "The National School of Teacher" for training of candidates of teachers in subject groups of schools with low number of students. | LEPL National Center for Teacher Professional Development, institutions of higher education, schools. |  | 2019 | 4850000 | The state budget
| 1.2 Increase of prestige of the profession by means of media campaigns, ceremonies of awarding the winners of teachers' competitions. | Media plots on the positive aspects of the profession of teacher; at least one competition for determining the best teacher (by subjects); the best teacher and the best principal 2019 of public school. | The Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Teacher Professional Development | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Teacher Professional Development; educational institutions; private sector; non-governmental organizations; media. | 2019 | 150000 | The state budget
2. Creation of environment of continuous education opportunities and increase of motivation of teachers | 2.1 Providing necessary resources for the professional development of teachers | Various printed and online resources are available for teachers; the number of downloads from the onlile gazette "mastsavlebeli.ge" is increased by 10%. | LEPL Educational and Scientific Infrastructure Development Agency; The Ministry of Education, Science, Culture and Sport of Georgia | HEIs, associations, non-governmental organizations | 2019 | 565000 | The state budget
| 2.2 Promotion of comprehensive development of professional skills of teachers. | The scheme of professional development and career growth is improved; the draft version of the "Rule of Regulation of Teacher's Profession" is developed; engagement of teachers in the professional development is increased by 10%. | LEPL National Center for Teacher Professional Development |  | 2019 | 1630000 | The state budget
| 2.3 Continuation of facilitating the decentralization of the professional development. | Receiving final reports from five winner grant projects. The "Provision on Registration and Fee of Educational Programs of Teachers' Professional Development" was elaborated. Is sent for approval to the Ministry of Education, Science, Culture and Sport of Georgia. | The Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Teacher Professional Development | Associations, institutions of higher education, non-governmental organizations | 2019 | 100000 | The state budget
| 2.4 Support of teachers, school administrations and parents of schools for national minorities (where the projects of the National Center for Teacher Professional Development are not implemented), with the purpose of learning the state language. | The courses of the state language are available for teachers and principals, as well as for parents. | LEPL - Zurab Zhvania State School of Administration | Institutions of higher education | 2019 | 600000 | The state budget
3. Establish a mechanism for attraction, retaining and motivation of school management/administration/technical personnel | 31. Increasing sallary minimum/maximum of school principals | increase rate | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 4500000 | The state budget
3.2. Increasing remunaration of school management/administrationtechnical personnel
4. Establish a mechanism for attraction, retaining and motivation of teachers | 4.1 Implementation of effective recruiting mechanisms of hiring/firing the teachers. Activation of the pilot regime of the candidacy program. | The rule of registration of candidates for teachers was developed; The registration portal of candidates for teachers was established; The program of candidacy for teacher is established; the number of teachers involved in this program. | The Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Teacher Professional Development |  | 2019 | Administrative resource | The state budget
| 4.2. In order to improve the remunaration of school teachers: a) state cash award are offerd to those teachers who reach the retirment age b) sallary over-heads are increased according to imrpoved status of the teacher; c) Teacher status related over-heads are increased. | a)number of retirment age teachers who received cash award; b) number of teachers benefited by increased sallary based on the improved status; c) teacher status overhead increase rate | The Ministry of Education, Science, Culture and Sport of Georgia; |  | 2019 | a) 75,000,000 b) 12,000,000 c) 15,500,000 | The state budget
5. Strategic Objective: Development of effective management system at all levels of general education
1. . Creation of school authorization mechanism and internal quality management system | 1.1 Developing effective mechanism of external and internal evaluation of schools. | The project of authorization standard for the institutions of general education is elaborated with the engagement of interested parties; the existing regulation of recognition was updated. | LEPL National Center for Educational Quality Enhancement; The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | Administrative resource | The state budget
| 1.2 Integration/expanding the information system of education management eSchool into the management of schools. | The system provides reflection of data for staff schedule of schools; the updated version of school electronic journal is developed. | LEPL Education Management Information System |  | 2019 | 1020 | The state budget
| 1.3 Development of practice of data collection and constant improvement of analysis. | The system of data visualization and reporting is active, which increases the availability of data for the decision-maker persons and improves the quality of analysis. With the purpose of facilitating the process of solving various spatial issues related to schools, the implementation of geoanalitical system commences. | LEPL Education Management Information System | MCA -Millennium Challenge Foundation - Georgia | 2019 | 273695 | The state budget (57,727 GEL); Financing from the partner (215,968 GEL)

## VET
Objective | Activity | Expected output | Responsible Entity | Partner entity | Implementation Period | Estimated budget | Funding Source
Specific Goal: Increase the number of vocational students to support the socio-economic development of the country and ensure their competitiveness through developing their vocational and general skills
1. Strategic Objective: Compliance of the vocational education with the requirements of labor market and internationalization of the system
1. Developing the Public Private Partnership | 1.1 With the purpose of imroving a vocational education, promoting involvement of a private sector. | The private sector has a possibility to participate in the following: In the implementation of programs based on work and training and retraining programs, including those with state financing; in the process of qualification development; in the councils or working groups established within the scope of vocational education; in the development of institutions within the format of public-private partnership | The Ministry of Education, Science, Culture and Sport of Georgia | Donor organizations (GIZ; UNDP); private sector | 2019 | Donor budget; administrative budget | Donor projects
| 1.2. Implementation of preparatory works for pilot testing the outsource of college management | Recommendations are worked out for pilot testing of college management outsourcing. | The Ministry of Education, Science, Culture and Sport of Georgia | Donor organizations (GGF); private sector | 2019 | Donors' budget | Donor projects
| 1.3. Facilitating development of colleges established within the scope of public-private partnership and/or development of new colleges. | The support for function of institutions established in the format of public-private partnership is implemented | The Ministry of Education, Science, Culture and Sport of Georgia | private sector | 2019 | 1750000 | The state budget; private sector
| 1.4. Facilitating implementation of work-based teaching/dual programs. | The number of programs based on work/dual programs is increased (at least 1 new sphere is added and at least 600 students are engaged in the programs). | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | Donor organizations (GIZ; UNDP); private sector | 2019 | 200000 | The state budget; Donor projects; private sector
| 1.5. Implementation of training and retraining programs within the framework of public-private partnership. | At least 30 private companies are involved in the implementation of training and retraining programs. | Ministry of Education, Science, Culture and Sport of Georgia | Donor organizations (UNDP, GIZ); private sector | 2019 | 500000 | The state budget; private sector
2. Development and implementation of mechanisms of compatibility with European educational area, recognition and mobility of professional qualifications existing in Georgia; | 2.1 ​Implementation of new qualifications framework, compliant with the European Qualifications Framework. | The qualifications corresponding to the new National Qualifications Framework are available for students. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement | Donor organizations (EU); | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
| ​2.2 Defining and approving documents confirming vocational education and forms of their annexes (according to EUROPASS). | The forms of documents confirming vocational education and their annexes are defined and approved (according to EUROPASS). | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement | Donor organizations | 2019 | administrative budget | The state budget; Donor projects
| 2.3. Conducting a situation analysis in relation to teaching the English language and providing the respective recommendations | In the vocational educational institutions, the respective analysis is conducted and the recommendations are worked out on the necessary actions/resources. | Ministry of Education, Science, Culture and Sport of Georgia | Donor organizations (GGF); | 2019 | Donors' budget | The state budget; Donor projects
3. Develop vocational qualifications relevant to the labor market requirements | 3.1.​ Formation/update of vocational qualifications with the participation of employers and facilitating implementation | Vocational qualifications are formed according to the demand from employers, the support of institution in implementation is ensured. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement | private sector | 2019 | 151800 | The state budget; private sector
| 3.2. Establishment and development of electronic system/registry of vocational qualifications and ensuring their availability. | The electronic system/registry of vocational qualifications is established. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | private sector; | 2019 | 20000 | The state budget; private sector
4. Develop and implement effective mechanisms of quality assurance; | 4.1 Updating the existing mechanisms of quality assurance and implementation of new evaluation system based on outcomes (standards and procedures of institutional and program evaluation; monitoring; self-evaluation). | New standards of authorization are developed and approved; the authorization provision is updated. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement | Donor organizations (UNDP; ETF); | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
| 4.2 Development of institutional capabilities based on the updated quality assurance system. | Informational/consultation meetings are held (at least 5) with the parties engaged in the process of quality assurance. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement | Donor organizations (UNDP) | 2019 | 20000 | The state budget; Donor projects
5. Promote continuous professional development of vocational education teachers and attract new staff; | 5.1 Implementation of preparatory works with the purpose of training teachers of vocational education, developing a new model for entry into profession and continuous professional development. | The standard of teacher of vocational education and qualifying requirements are developed. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Teacher Professional Development | Donor organizations (GGF; World Bank) | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
| 5.2 Development of international collaboration and sharing a best international practice with the purpose of teachers' professional development. | Administrations and teachers of at least 5 educational institutions are involved in the process of sharing an international practice. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Teacher Professional Development | Donor organizations (GIZ) | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
| 5.3 Conducting preparatory works with the purpose of facilitating implementation of the new scheme of labor remuneration of teachers. | The vision of diversified system of labor remuneration of teachers is developed. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Teacher Professional Development | Donor organizations (GGF; World Bank) | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
6. Introduction of entrepreneurial teaching for graduate employment and self-employment; | 6. 1. Determination of models of entrepreneurship education and innovative teaching and their pilot implementation | In the process of entrepreneurship teaching, the new innovative approaches are implemented in the pilot regime. | Ministry of Education, Science, Culture and Sport of Georgia; educational institutions | Donor organizations (ETF; UNDP) Agency for Innovations and Technologies of Georgia | 2019 | Donors' budget | The state budget; Donor projects; private sector;
| 6.2. Improvement of entrepreneurship teaching for the students of vocational education. | The entrepreneurship module was reviewed/updated; Workshops/working meetings and conferences are organized with the purpose of improving the quality of entrepreneurship teaching (at least 4 for the year). | Ministry of Education, Science, Culture and Sport of Georgia; educational institutions | Donor organizations (ETF, UNDP; US embassy) Agency for Innovations and Technologies of Georgia | 2019 | Donors' budget | The state budget; Donor projects; private sector;
7. Development of information system of management of vocational education and training (eVet). | 7.1 Development of information system of management of vocational education and training (eVet). | The vision document of information system of management of vocational education and training (eVet) is created; business processes are described, considering the amendments in legislation. Program modules of educational institution, educational programs and human resources are created. | LEPL Education Management Information System; Ministry of Education, Science, Culture and Sport of Georgia | LEPL National Center for Educational Quality Enhancement | 2019 | 265725 | The state budget (from the unified resource of the LEPL LEPL Education Management Information System)
2. Strategic Objective: Ensuring access to life long learning based vocational education
1. Connecting vocational education with other education levels and overcoming of educational gaps | ​1.1. Agreeing on approach on "integration" of learning outcomes of intermediate stage of general education into the vocational education, and its reflection in the regulating acts. | The approach on "integration" of learning outcomes of intermediate stage of general education into the vocational education is developed and reflected into the regulating acts. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | Donor organizations (UNDP) | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
| 1.2. Determination of requirements in relation to the obtaining a right to implement the integrated program by an educational institutiion and formalization of the procedure | The rule of obtaining a right to implement the integrated program is determined. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; | Donor organizations (UNDP) | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
| 1.3. Development/approval of the model of students evaluation (in the part of full general education) within the scope of "integrated" programs. | The approach to the evaluation within the scope of "integrated" programs is developed. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | Donor organizations (UNDP) | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
| 1.4. Conducting preparatory works for commencing the implementation of integrated programs. | Preparatory works are completed (selection of teachers, development of curricula, authorization, etc.) for commencing the implementation of integrated programs. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | Donor organizations (UNDP) | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
| 1.5. Conducting preparatory works for implementation of short-cycle programs. | Preparatory works are conducted for commencing the pilot testing of short-cycle programs: the concept of short-cycle programs is worked out, the agreement is reached on the regulating framework and methodology of short-cycle programs; the approach to obtaining a right on implementation of short-cycle programs is defined. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | Donor organizations (GGF) | 2019 | Donors' budget; administrative budget | The state budget; Donor projects
| 1.6. Based on the updated legislation, development of the vision for creating possibility to recognize credits received in vocational education, within the scope of the first stage of academic education. | The vision is elaborated (it is reflected in the regulation for credits, regulation of recognition of formal education, regulation for development of educational standard) for allowing possibility to recognize credits received in the vocational education at the stage of academic education. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | 2019 | Administrative resource | The state budget;
2.Create flexible curriculum, models and services relevant to the needs of various target groups, including adults; | 2.1. Determining the respective approaches and regulations for the formation of the system of training and retraining (determination/formalization of the approach to obtaining a right, determination of the procedure for development of programs, determination of the enrollment procedure, determination of the mechanism of financing, development of the respective technical platform). | Appropriate approaches and regulations are developed and approved for the formation of a training and retraining system within the scope of vocational education; the respective electronic platform functions for the administration of processes. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Education Management Information System | Donor organizations (UNDP) | 2019 | 2000000 | The state budget; Donor projects
| 2.2. Commencing implementation of votational training and retraining courses and their monitoring. | According to request, the programs of professional training and retraining are conducted; the monitoring of the programs of professional training and retraining is implemented. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | Donor organizations (UNDP) | 2019 |  | The state budget; Donor projects
| 2.2 Implementation of educational programs focused on the needs of various target groups (disabled persons/with special educational needs, refugees, socially vulnerable persons, etc.), and introduction/development of additional services. | The additional services are provided for various target groups, according to the needs (educational resources, special teachers, student dormitories). | Ministry of Education, Science, Culture and Sport of Georgia; educational institutions |  | 2019 | 1500000 | The state budget;
3. Creating and developing effective mechanisms for recognition of formal and informal education | 3.1 Based on the updated legislation, creating a possibility to recognize competencies acquired in formal education, for the purposes of other program. | The procedure of recognition of competencies acquired in the formal education is developed. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions |  | 2019 | Administrative resource | The state budget;
| 3.2 Based on updated legislation, implementation of methodology, service and monitoring of recognition of non-formal education. | The procedure of recognition of nonformal education is approved; recognition of nonformal education commences within the scope of identified priority sphere/spheres. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL National Center for Educational Quality Enhancement; educational institutions | Donor organizations (UNDP) | 2019 | 63,500.00; Donors' budget | The state budget; Donor projects
4. Creating diversified financing mechanisms; | 4.1 Development of the vision for the outcome-oriented flexible model of financing. | The analysis of existing model of financing was conducted and the vision of new model is worked out. | The Ministry of Education, Science, Culture and Sport of Georgia | Donor organizations (GGF) | 2019 | Donors' budget | The state budget; Donor projects
5. Creating a unified, universally accessible and flexible network of vocational educational institutions (state and private) | 5.1 Improving a geographic coverage of vocational educational institutions. | The number of providers of vocational education is increased - at least 1 new institution. | The Ministry of Education, Science, Culture and Sport of Georgia | private sector; | 2019 | 10000000 | The state budget; private sector
| 5.2. Creating possibilities for receiving vocational education in schools - development of infrastructure, human resources, etc. | In public schools (at least 500 schools) the certification courses for vocational training are implemented (within the scope of nonformal education). | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 500000 | The state budget; Donor projects
| 5.3 Conducting preparatory works for the purpose of development of Excellence-center | The concept of development of the Excellence-center was prepared; for the establishment and functioning of the center (designing, construction, management), the respective consulting center is selected. | The Ministry of Education, Science, Culture and Sport of Georgia | Donor organizations (KFW) | 2019 | Donors' budgett; administrative budget | The state budget; Donor projects
| 5.4 Diversifying the providers of vocational education by means of development of stimulating mechanisms | The network of providers of vocational education is diversified - vocational education is provided by educational institutions (colleges, schools, universities), as well as by companies - in real work environment, sector-specific associations and other authorized organizations. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | administrative budget | The state budget; private sector; donor organizations
3. Strategic Objective: Promoting vocational education and increasing its attractiveness
1. Develop vocational orientation and career planning service | 1.1 Commencing works for the purpose of establishing a unified model of vocational orientation and career planning. | The implementation of the respective project is started, with the purpose of development of vocational orientation, consulting and career planning (the project of EU technical assistance) | Ministry of Education, Science, Culture and Sport of Georgia; educational institutions | Donor organizations (EU); | 2019 | Donot budget | The state budget; Donor projects
| 1.2Promoting implementation of the component of vocational education in schools. | School students are engaged in the activities developing vocational skills - at least 5000 students; the scope of the "Program of Development of Vocational Skills in School Students" is increased; The vision of sustainability of the program is defined. | The Ministry of Education, Science, Culture and Sport of Georgia | Educational institutions | 2019 | 3500000 | The state budget;
2. Develop vocational orientation and career planning service | 2.1 Conducting an information campaign, including in accordance with the new communication strategy. | Conducted events and number; the increased number of persons interested in receiving vocational education. | The Ministry of Education, Science, Culture and Sport of Georgia | Donor organizations (GIZ) social partners | 2019 | Donors' budget; administrative budget | The state budget; Donor projects

## HE
Objective | Activity | Expected output | Responsible Entity | Partner entity | Implementation Period | Estimated budget | Funding Source
Specific Goal: Internationalization of higher education and ensuring access to quality higher education to improve individual's personal and professional development and employment
Strategic Objective 1. Further modernization of Higher Education System, promotion of internationalization and quality improvement
1. Improve learning and teaching quality in higher education system. | 1.1 Creating and implementing the programs of professional development of personnel implementing educational programs. | The number of academic and administrative personnel participating in the international mobility; The number of academic and administrative personnel participating in trainings, working meetings and conferences. | The Ministry of Education, Science, Culture and Sport of Georgia | LEPL International Center of Education, LEPL National Center for Educational Quality Enhancement, institutions of higher education, Erasmus+ National Office | 2019 | 150000 | The state budget donors' projects; HEIs budget
| 1.2 Connecting with higher education institutions after graduates from the international education center return to their country, including in specific studying subjects. | The number of returned graduates involved in educational and scientific processes. | The Ministry of Education, Science, Culture and Sport of Georgia | LEPL International Center of Education | 2019 | 50000 | The state budget
2. Internationalization of Higher Education System of Georgia | 2.1 Implementation of programs facilitating to international mobility of students and studying abroad. | The number of students participating in the program of international mobility and financed with the purpose of studying in a foreign educational institution. | Ministry of Education, Science, Culture and Sport of Georgia | LEPL International Center of Education, Erasmus+, donors | 2019 | 6194600 | The state budget donors' projects
| 2.2. Development of joint academic programs together with international partners | Increased number of joint academic programs developed together with the international partners. | HEIs, Ministry of Education, Science, Culture and Sport of Georgia | Erasmus+ | 2019 | Administrative resource; | The state budget donors' projects
3. Creating effective and efficient funding system | 3.1 Identifying effective and efficient model of financing in collaboration of the international partners/experts, based on local social and economic factors. | The research on HE funding models was carried out. Disscussions for approval of the most relevant model are going on. | The Ministry of Education, Science, Culture and Sport of Georgia | HEIs; World Bank | 2019 | Administrative resource; WB technical assistance | The state budget; donors' projects
4. Automation of business processes occurring in the sphere of higher education. | 4.1. Digitalization of the process of enrolment announcement on the programs of higher education. | Electronic questionnaires are introduced for enrolment on the programs of higher education. | LEPL Education Management Information System, LEPL National Assessment and Examination Center | Ministry of Education, Science, Culture and Sport of Georgia, HEIs | 2019 | Administrative resource;(Resource of EMIS ) | The state budget
| 4.2 Creating and developing the automated software - Uni-Grants for calculation of grant and program financing. | The system Uni-Grants is functioning. | LEPL Education Management Information System | HEIs | 2019 | Resource of EMIS | The state budget
| 4.3 Starting works on creating a management information system of higher education (eUni). | The description of business processes was carried out, taking into consideration the amendments in the legislation; the Terms of Reference is developed; formation of program part of the system is started. | The Ministry of Education, Science, Culture and Sport of Georgia | LEPL National Center for Educational Quality Enhancement, LEPL Education Management Information System | 2019 | Resource of EMIS | The state budget
5. Establishment of results and development oriented quality assurance system | 5.1 Evaluation and monitoring of institutions of higher education in accordance with authorization standard and procedures compatible with the ESG. | 12 institutions evaluated according to authorization standards and procedures compatible with the ESG. | LEPL National Center for Educational Quality Enhancement | HEIs | 2019 | 2150000 | The state budget; donors' projects
| 5.2 Evaluation and monitoring of programs of higher education in accordance with authorization standard and procedures compatible with the ESG. | 200 educational programs evaluated according to accreditation standards and procedures compatible with the ESG. | LEPL National Center for Educational Quality Enhancement | HEIs | 2019
| 5.3 Refining and developing standards and procedures of authorization of higher education institutions and accreditation of higher education programs. | The document of analysis on the shortcomings revealed in the standards and procedures of authorization and accreditation is elaborated and the respective projects are initiated. | LEPL National Center for Educational Quality Enhancement | The Ministry of Education, Science, Culture and Sport of Georgia | 2019
| 5.4 Involvement of international experts, students and employers in the processes of authorization and accreditation. | Authorization and accreditation visits carried out with the participation of the international experts, students and employers. | LEPL National Center for Educational Quality Enhancement | HEIs, European agencies for higher education quality ensurance | 2019
| 5.5. Ensuring implementation of supporting measures for the higher education institutions in relation to the standards and procedures of authorization and accreditation. | 2 tutorials are updated and developed; 8 training modules are elaborated; up to 1000 persons are retrained; 5 working meetings/trainigs. | LEPL National Center for Educational Quality Enhancement | The Ministry of Education, Science, Culture and Sport of Georgia | 2019 | 855000 | The state budget; donors' projects
| 5.6 Implementation of quality assurance electronic system (QMS) for institutions of higher education and monitoring on it. | Electronic system of authorization process of for institutions of higher education is functioning. | LEPL National Center for Educational Quality Enhancement | HEIs, LEPL Education Management Information System | 2019
| 5.7 Development of internal quality assurance tutorial for 7 HEIs. | The tutorial of internal quality assurance is developed and uploaded on the webpage of the LEPL - National Center for Educational Quality Enhancement - ege.gov.ge. | LEPL National Center for Educational Quality Enhancement | HEIs; Ministry of Education, Science, Culture and Sport of Georgia | 2019
| 5.8 Ensuring implementation of recommendations developed by the ENQA experts. | a) Recommendations are reflected in the Action Plan of the National Center for Educational Quality Enhancement; b) number of Amendments made into two legal acts; | LEPL National Center for Educational Quality Enhancement | The Ministry of Education, Science, Culture and Sport of Georgia | 2019
| 5.9 Collaboration with the quality assurance agencies, members of Germany and Estonia ENQA in relation to quality assurance issues of higher education within the scope of EU project Twinning. | 20 international experts from quality assurance agencies of 2 institutions of higher education - members of ENQA, in at least 7 sectors. | LEPL National Center for Educational Quality Enhancement | The Ministry of Education, Science, Culture and Sport of Georgia | 2019
| 5.10 Development of sectoral benchmarks (based on the updated "Establishment of Sectoral Councils of Higher Education and Procedures of their Activity and methodology of compliance of learning outcomes with the National Qualifications Framework level) and facilitating implementation of approved sectoral benchmarks. | Approved: sectoral councils and working groups; updated/developed: sectoral benchmarks of regulated/non-regulated specialties, the regulation on developing, updating and approving sectoral benchmark of higher education, sectoral councils, creation and activities of sectoral working groups; the methodology of compliance of educational programs with the level of National Qualifications Framework is developed and implemented. | LEPL National Center for Educational Quality Enhancement | HEIs, Donors | 2019 | 30 619.00 | The state projects; donors' projects
| 5.11 Preparation of self-sertification of National Qualifications Framework. | 2020-2021 action plan of referencing established within the scope of Twinning project, in accordance with 10 principles of European Qualifications Framework. | LEPL National Center for Educational Quality Enhancement | Donors | 2019 | 50000 | The state budget; donors' projects
2. Strategic Objective: Creation of efficient, lifelong learning opportunities
1. Recognition of distance education | 1.1 Development of mechanism to ensure quality asurance of remote education recognition. | The draft package of amendments into the legislation on mechanisms of quality assurance of remote education recognition is developed. | LEPL National Center for Educational Quality Enhancement, Ministry of Education, Science, Culture and Sport of Georgia | Donors | 2019 | Administrative resource; | The state budget donors' projects
3. Strategic Objective: Increase access to quality education
1. Providing quality inclusive higher education | 1.1. Financing various vulnerable groups of students with state studying and master's grants. | The number of financed students: a) up to 200 students, graduated from the schools of high mountainous region; b) up to 150 students from the occupied territories; c) up to 20 students, graduated from non-Georgian language schools; d) Heirs of veterans fallen in the fight for territorial integrity, missing persons, veterans with serious disabilities and theit children - up to 40 students; e) up to 5 students having a status of repatriate; ) orphan(orphaned) - up to 50 students; f) up to 100 students, members of large families; g) up to 40 students - disabled persons; h) up to 50 students - graduates from schools of the villages adjacent to the dividing line; i) up to 16 students - under the state care; j) up to 500 students - socially vulnerable (70000 rating score and less); k) 5 students with disorders of autism specter. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 2725000 | The state budget
| 1.2 Financing damaged students living in the villages adjacent to the dividing line. | The number of financed students. In the second semester of 2018-2019, 1635 students will be financed; in the first semester of 2019-2020, up to 1780 students will be financed. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 3723000 | The state budget
| 1.3. Providing successful students of higher education institutions (LEPLS) with scholarships. | a) Up to 2701 students will be provided with scholarship; b) Dimitri Gulia and Kosta Khetagurov scholarships will be granted to 2 students in 2018-2019 academic year, and in the first semester of 2019-2020 academic year - additionally to 2 students (in total 4 students). | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 4100000 | The state budget
| 1.4 Facilitating convicted persons in receicing a higher education. | The number of convicted persons determined by the joint Order №72/№ 30/n of the Minister of Penitentiary System and Probation and the Minister of Education and Science, who, in the result of Unified National Examinations, obtained the right to study in HEIs. Implemented amendments into legislation for continuation of study on master's programs. | Ministry of Education, Science, Culture and Sport of Georgia, LEPL National Assessment and Examination Center; LEPL Education Management Information System | HEIs | 2019 | Administrative resourses | The state budget
| 1.5. Financing those persons with state grants, who received higher education on the territories of Abkhazia Autonomous Republic and former South Ossetia Autonomous District and continue studying in Georgian HEIs. | a) The number of financed students: 8 students enrolled in Georgian HEIs will be financed after recognition of higher education received on the occupied territories; b) The number of persons participating in training program for post-school education - 139. | Ministry of Education, Science, Culture and Sport of Georgia, LEPL National Assessment and Examination Center; LEPL Education Management Information System Respective educational resource centers | HEIs | 2019-2020 | 532750 | The state budget
| 1.6 Implementation of the program of training for post-school education. | The number of persons participating in training program for post-school education - 139. | Ministry of Education, Science, Culture and Sport of Georgia; | HEIs

## SCI
Objective | Activity | Expected output | Responsible Entity | Partner entity | Implementation Period | Estimated budget | Funding Source
Specific Goal: Modernization and internationalization of science, technology and innovation System for creating new knowledge and promoting sustainable development of the country.
1. Strategic Objective: Development of Eco System of Science, Technology and Innovation (STI) of Georgia to achieve distinguished quality in science and technology
1. . Improve the legislative basis for management of science, technology and innovation (STI) system for strengthening international investments in intellectual property rights, technology transfer, and science, technology and innovation (STI) sectors | 1.1. Initiating amendments into the Law of Georgia on Science, Technologies and their Development. | Amendments, in relation to carrying out investment in the STI sphere, reviewed with the respective interested parties (ministries, LEPLs and research universities) and submitted to the parliament for approval. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | Ministry of Economy and Sustainable Development of Georgia, Georgian Agency for Innovations and Technologies - GITA, IPR National Center - Sakpatenti | 2019 | Administrative resource | The state budget
| 1.2. Initiating amendments into the Law of Georgia on the Higher Education. | Amendments, in relation to carrying out investment in higher education, reviewed with the respective interested parties (ministries, LEPLs and research universities) and submitted to the parliament for approval. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | Ministry of Economy and Sustainable Development of Georgia, Georgian Agency for Innovations and Technologies - GITA, IPR National Center - Sakpatenti | 2019
| 1.3. Initiating amendments into the law of Georgia on Innovations. | Amendments, in relation to facilitating IPR and technology transfer (university-industry cooperation), reviewed with the respective interested parties (ministries, LEPLs and research universities) and submitted to the parliament for approval. | Georgian Agency for Innovations and Technologies; Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | Ministry of Economy and Sustainable Development of Georgia, IPR National Center - Sakpatenti | 2019
| 1.4. Initiating amendments into the law of Georgia on Grants. | Amendments, in the sphere of STI, in relation to facilitating university-industry cooperation, reviewed with the respective interested parties (ministries, LEPLs and research universities) and submitted to the parliament for approval. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | Ministry of Economy and Sustainable Development of Georgia, Georgian Agency for Innovations and Technologies - GITA. | 2019
2. Modernization and updating of Science, Technologies and Innovations (STI) Infrastructure and research opportunities in Georgian research universities, integrated scientific-research institutes and independent research centers. | 2.1. Development of scientific and research infrastructure by the Ministry of Education and Science of Georgia. | The program "Development of Infrastructure of Higher Education and Scientific Institutions" is worked out and approved. | The Ministry of Education, Science, Culture and Sport of Georgia |  | 2019 | 8211000 | The state budget
3.. Optimization of career development mechanisms in Science, Technology and Innovation (STI) sector for the development of internationally competitive human resources | 3.1. Issuing state scientific grants by means of competition and facilitating scientific researches. | a) Administering up to 20 state grant competition; b) improvement/development of existing state grant competitions; c) elaboration/development of new schemes of grant financing. | Ministry of Education, Science, Culture and Sport of Georgia; Shota Rustaveli National Scientific Foundation |  | 2019 |  | The state budget (Administrative resource)
| 3.2. Supporting high quality scientific researchers in Georgia. | a) For the fundamental, applied researcher with the participation of Georgians working abroad (FR, AR, DI), no less than 70% of the project will be financed; b) within the scope of scientific programs, studying Georgia - no less than 6 projects will be financed; c) to strengthen the participation in the international framework programs - no less than 4 projects will be financed. | Ministry of Education, Science, Culture and Sport of Georgia; Shota Rustaveli National Scientific Foundation |  | 2019 | 13885667 | The state budget
| 3.3. Supporting development of scientific career of young scientists and integration into research universities. | a) Based on the grant competition, up to 80 research projects of talented young researchers (master students, doctoral students, and postdoctoral researchers) were financed; b) up to 36 projects for the collaboration of master students, doctoral students, and postdoctoral researchers from Georgia with the foreign institutions of higher education and scientific research institutions (DAAD, Juelich) were financed; | Ministry of Education, Science, Culture and Sport of Georgia; Shota Rustaveli National Scientific Foundation | Juelich Research Center of Germany, German Academic Exchange Service | 2019 | 3543027 | The state budget; donors' projects
| 3.4. Facilitating scientific mobility and organization of scientific events. | Up to 90 beneficiaries of scientific mobility and grant competition of scientific events. | Ministry of Education, Science, Culture and Sport of Georgia; Shota Rustaveli National Scientific Foundation |  | 2019 | 1277330 | The state budget
| 3.5 Development of special competitive scheme of financing for attracting, retaining and integrating highly qualified scientists and young personnel into the research universities and centers. | The participation of at least one young scientist (who received education abroad and works with international research centers) in the research project in Georgia was financed. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | Juelich Center | 2019 | 411000 | The state budget; donors' projects
| 3.6. Supporting academic and scientific personnel, as well as development of entrepreneurial skills of students, creative and business thinking at all stages of formal and nonformal education, with the purpose of integration of research into entrepreneurial activity and commercialization of science. | Grants supporting the collaboration between EaP * BSH countries (scientific grants, mobility, joint conference/seasonal school). Programs of large-scale intermediate events (grants, target topical events). | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation, Georgian Agency for Innovations and Technologies - GITA, CRDF Global, | EU Framework Program of Research and Innovations from EU delegation in Georgia | 2019 | 408000 | The state budget; donors' projects
4. Supporting the integration of research and educational programs in the educational programs of research universities with active application of the infrastructure and human resources of research institutions and centers. | 4.1. Facilitating development of national structured doctoral programs and joint doctoral programs in collaboration with international partners. | 8 ongoing national structured doctoral programs selected on the basis of grant competition and 4 Georgian-German structured doctoral programs (PhD) are financed. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | Volkswagen Foundation, Germany | 2019-2021 | 1360083 | The state budget; donors' projects
| 4.2. Financing joint research traineeship together with international partners (scholarships of DAAD - Rustaveli Foundation for doctoral students and postdoctoral researchers). | Research traineeship of up to 30 doctoral students and up to 30 postdoctoral researchers in the research universities of Germany with joint scholarship program of DAAD - Rustaveli Foundation. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | DAAD, Germany | 2019 | 880000 | The state budget; donors' projects
| 4.3. Financing young researchers (research grants for postdoctoral researchers). | Up to 100 scientific projects of postdoctoral researchers are financed in research universities and centers of Georgia, in all scientific fields defined by Eurostat classificator. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | 870000 | The state budget;
| 4.4. Financing doctoral students (research grants for doctoral students). | Up to 100 scientific projects of doctoral students are financed in research universities and centers of Georgia, in all scientific fields defined by Eurostat classificator. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | 678000 | The state budget;
5 Supporting the integration of research and educational programs in the educational programs of research universities with active application of the infrastructure and human resources of research institutions and centers. | 5.1. Integration of Key Performance Indicators of Science, Technology and Innovation (STI) system into the systems of quality assurance of educational programs and human resources management. | ELSEVIER databases (Scopus, Science Direct, Scivalfunding are available for the consortium consisting of 54 institutions and Expert Lookup base foundation); conducted trainings/consultations on the use of these bases, including with the purpose of STI analysis and evaluation. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | 1332800 | The sum returned from H2020
6. Promote strategic priority sectors and relevant financing in the field of science, technology and innovation (STI) aimed at sustainable development of the country. | 6.1. Starting a dialogue between the persons interested in the system of science, development and innovations, including with the engagement of governmental, academic, public and private sectors. | One international forum was held, up 10 10 round tables and working meetings. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | The Ministry of Economy and Sustainable Development, Research and Innovation Council | 2019 | 100000 | The state budget;
| 6.2. Development of action plan with the purpose of facilitating sectoral dialogue in the field of science, modernization of scientific policy and reforming a research system in the country, and with the purpose of implementation of recommendations elaborated within the scope of EU Horizon 2020 Policy Support Facility (H2020 PSF), . | The detailed action plan, elaborated in accordance with the recommendations of H2020 PSF mechanism; validation of the action plan by the representatives of European Commission. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | The Ministry of Economy and Sustainable Development; Innovations and Technologies Agency of Georgia; Research and Innovation Council | 2019 | Administrative resource | The state budget
7. Development and implementation of science, technology and innovations (STI) programs and financing schemes focused on protection and promotion of Georgian culture and national identity. | 7.1. Elaboration of open competition financing schemes with the purpose of research and popularization of cultural and material heritage of Georgia. | 5 grant projects financed for the research of cultural and material heritage of Georgia, existing abroad and on the territory of the country. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | 752913 | The state budget;
| 7.2. Supporting the target international conferences and seasonal schools of popularization of sciences studying Georgia. | Grant competition conducted for the popularization of sciences studying Georgia and no less than 4 financed projects. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | 94538 | The state budget;
| 7.3. Development and implementation of target project with the purpose of establishing an international interdisciplinary center of sciences studying Georgia. | The concept of the international interdisciplinary center of sciences studying Georgia is developed and reviewed together with stakeholders (ministries, research universities and institutions/centers). Development guideline is worked out. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | Ministry of Economy and Sustainable Development of Georgia, National Museum of Georgia, main research universities and independent research centers (with profile of studying Georgia). | 2019 | Administrative resource | The state budget
2. Strategic Objective: Strengthening the role, status and value of science, technology and innovation (STI) in the country and positioning it as a strategically important national priority for the country.
1. Promoting science, technology and innovation (STI) at every level of formal and informal education | 1.1. Development of the program of scientific festival. | Scientific events and workshops carried out with the participation of prominent Georgian scientists, workshops within the scope of the annual scientific festival and the number of municipalities/participants in these events. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | 400000 | The state budget;
| 1.2. Popularization of distinguished scientists. | Recognition of distinguished achievements and contribution of researchers in Georgia in science and technologies, and, for popularization of sciences studying Georgia, supporting foreign scientists working in this sphere by means of annual awards and scholarships. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | 85000 | The state budget;
| 1.3. Supporting young scientists working in research or authorized institutions of higher education of Georgia, with the purpose of promoting science and promoting role and importance of scientists in the broad society. | No less than 7 personal scholarships will be granted within the scope of grant competition of personal scholarships for young scientists. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | 85000 | The state budget;
| 1.4. Implementation of target programs and projects in schools with the purpose of promotion and communication of science, technologies and innovations (STI). | Television and radio broadcasting best achievements of scientists based on the collaboration between the Shota Rustaveli National Scientific Foundation and National Geografic (Georgia), with the purpose of STI promotion. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | The publishing house National Geografic | 2019 | 100000 | The state budget;
| 1.5 Supporting scientific publications and journals. | State scientific grants for international publications, the scientific journal. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | 200000 | The state budget;
2. Promoting research competencies and innovative thinking, promoting scientific ethics at each stage of formal and informal education. | 2.1. Facilitating schemes of financing young inventors and researchers by means of open grant competition procedure for the school students (Leonardo da Vinci competition) and for the joint research projects of school students and teachers from HEIs, with the engagement of school students. | a) The number of granted awards for young inventors and researchers within the scope of open grant competition "Leonardo da Vinci" administered by the Shota Rustaveli National Scientific Foundation; b) the number of projects of school students and academic personnel of HEIs financed on the basis of annual grant competition . | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | TBC Bank | 2019 | 135000 | The state budget; donors' projects
| 2.2. Improvement of research infrastructure of STEM subjects in public schools and facilitating research skills, innovative thinking and integration of research ethics into curriculum. | Administering bilateral programs, including joint research projects, mobility and collaboration in scientific events (CNR, CNRS PICS, STCU, ISTC, TUBITAK, BAR-ILLAN, etc.). | The Ministry of Education, Science, Culture and Sport of Georgia | MCC, TPDC | 2019 |  | The state budget(Administrative resource)
3. Strategic Objective: Internationalization of Science, Technology and Innovation (STI) System and Diversification of Financing Resources
1. Strengthening participation of Georgian researchers and institutions in the EU Research and Innovation Program (Horizon 2020) and financing schemes of other international agencies. | 1.1 Raising awareness of Georgian scientists on the competitions announced within the scope of Horizon 2020 programme and on conditions of participation in them. | 7 informational events and up to 100 consultations conducted on the topics related to the grant competitions of Horizon 2020. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | Administrative resource | The state budget;
| 1.2. Supporting successful participation of Georgian scientists in H2020 competitions and integration into the international scientific field. | Elaboration and pilot testing the competition of scientific traineeship of Georgian researchers together with the scientific head of European Research Council (ERC) grant; Preparatory grants of the EU Framework Programme for Research and Innovation - Horizon 2020; joint grants together with French Institute. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | ERC, French Institute | 2019 | 207650 | The state budget, donors' projects
| 1.3. Organizing informational days, improvement of webpage; facilitating participation in grant competitions of Research and Innovation Framework Program. | Raised awareness on EU programs, increased number of participants, increased index of success in the projects/programs. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | Universities, research centers; GITA | 2019 | Administrative resource | The state budget; donors' projects
| 1.4. Development of grant programs supporting researchers' mobility, which would create such possibilities for Georgian scientists and researchers that would help them to strenghten connections with European scientific circles. | Terms of Reference developed with the purpose of selection of the organization, implementing the grant program. | The Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation; | Delegation of EU in Tbilisi | 2019 | Administrative resource | The state budget
2 Promoting the implementation of international, long-term cooperation instruments and programs in the Science, Technology and Innovation (STI) system of Georgia. | 2.1. Facilitating development of international collaboration in scientific researches. | Administering bilateral programs, including joint research projects, mobility and collaboration in scientific events (CNR, CNRS PICS, STCU, ISTC, TUBITAK, BAR-ILLAN, etc.). | Ministry of Education, Science, Culture and Sport of Georgia; LEPL - Shota Rustaveli National Scientific Foundation, research universities. |  | 2019 | 1140249 | The state budget; donors' projects
| 2.2. Supporting engagement of Georgian researchers in the ongoing megaprojects of international research institutions/centers. | Annual membership fee for participation of Georgian scientists in the international organizations/research programs (CERN, DUBNA); up to 50 Georgian scientists are involved in the ongoing projects in CERN and DUBNA. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation, research universities. |  | 2019 | 1382810 | The state budget; donors' projects
| 2.3. Supporing association in the EU Framework Programmes for Research and Innovation (Horizon 2020). | Membership fee paid by Georgia for association into the Horizon 2020 programme. The increased number of projects with the participation of Georgia. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation, research universities. |  | 2019 | 5130030 | The state budget; donors' projects
| 2.4. Inclusion of Georgia into the EURAXESS programme of researchers' mobility and career development and establishing EURAXESS-Georgia network and its sustainable development. | The application for membership of Georgia into EURAXESS was submitted; designing EURAXESS-Georgia was carried out and events were held to attract financing. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation | Research universities | 2019 | 630000 | donors' projects
| 2.5 Institutional development of scientific foundation and deepening international collaboration. | The application was elaborated for Twinning instrument, for facilitating implementation of scientific policy and international standards of management in the scientific foundation. | Ministry of Education, Science, Culture and Sport of Georgia; LEPL Shota Rustaveli National Scientific Foundation |  | 2019 | Administrative resource | The state budget