Progress Report

Unified Strategy On Education and Science (2017-2021)

Vocational Education

2017-2018 years

2018

Table of Content

Summary	3

Strategy task 1: Compliance of vocational education with requirements of labour market and internationalization of the system	6

Strategic task 2: Ensuring the accessibility of vocational education, based on learning principal throughout the lifetime	11

Strategic task 3: Promotion of vocational education and increasing its attractiveness	16

Budget	18

Risks and the Ways of their Mitigation	19

Conclusion and Recommendations	20

The Action Plan (2017-2018) Fulfillment Report	22

## Summary

Unified Strategy on Education and Science (2017-2021), prepared in 2017, is based on the outcomes of ongoing reforms and the analyses of challenges in the field of Education and Science. The strategy covers the following directions of the system: early/preschool education, general, vocational and higher education as well as adult education, science and studies.  Strategy was approved with the Order of the Prime-Minister of Georgia (Order #533 07.12.2017) and has being implemented on bases of the relevant action plan.

Unified Strategy of Education and Science fully foresees the issues considered by the Association Agreement and its relevant Annexes made between Georgia and EU in the fields of education, retraining, youth, science, research and technological development. It also complies with the requirements of Bologna processes, recommendations of EU and Council of Europe in the direction of life long learning, as well as it complies with UN Sustainable Development Goals; The document also is in compliance with the priorities of Georgian Government and envisions the main principles of the social-economic development strategy of the country-“Georgia 2020”;

General goal of the strategy is the development of high quality education and science system based on the life-long learning principle, which provides all citizens of the country with equal opportunity to achieve sustainable learning outcomes.

One of the specific goals of the strategy is to increase the number of the vocational education students in order to support socio-economic development of the country, to ensure their competitiveness by means of developing technical and general skills. Three strategic tasks have been set in order to achieve this goal:

- Compliance of vocational education with requirements of labour market needs and internationalization of the system;

- Ensuring the accessibility to vocational education based on life-long learning principle;

- Promotion of vocational education and increasing the attractiveness.

In 2017-2018 significant progress was made in the direction of all three strategic tasks defined by the strategy:

New law on the Vocational Education was adopted in September 2018, aiming at (1) improving the quality and flexibility of the vocational education system, (2) establishing links with general, vocational and higher education, (3) integrating general education in the vocational education programs, (4) accumulation and transferring the credits; (5) development of adult educational system etc.  Next 2 years are defined for introduction of new law and consequently the year of 2019 will be the key, whereas the basic innovations determined by the law, will be systematized.  Government needs significant local resources as well as international support for efficient transformation of the system into new track.

Implementation of systemic changes in accordance with new legislation is closely linked with the adoption of new National Qualification Framework (NQF). Since 2014, government with local and international consultants intensively worked for the development of National Framework that would have been in compliance with European Qualification Framework. New structure and concept have been elaborated step by step with participation of stakeholders, leading to finalization of the document by the end of 2018. It is anticipated to adopt new NQF in the first quarter of 2019 (as it is defined by Georgian law “On the Education Quality”).

Significant work has been carried out in the direction of quality assurance of TVET sector. NCEQE intensively worked together with international organizations for preparation of new internal and external quality assurance framework. Significant contribution was made by EU and MCA TA projects. Piloting of internal and external verification approaches started in 2018 year and is planned to continue in 2019 with the aim to adopt new authorization standards by the end of 2019.

Three-year process of revision of TVET programs finalized in 2018. As a result, the system fully compiles competence-based modular vocational programs. Employers, representatives of Sectoral Associations/Unions were actively involved in the process of development of education standards. According to the law, from January 2019, all educational institutions will be eligible to receive students only on the modular vocational educational programs.

Since 2016, Georgia started introduction of Work Based Learning approach for insuring the relevance to labour market needs and improving the quality of teaching. Initially, the introduction of dual programs started in agriculture and viticulture sectors (2016) with the support of German and Swiss government funded projects. In 2017-2018, due to the increased interest from the side of private sector, the number of dual programs have been increased and according to the data of 2018, 23 types of dual programs have been introduced in the fields of agricultural, tourism, railway transportation, construction and engineering. Moreover, the preparatory work for upscaling the dual programs in the fields of IT, transport and logistics, is ongoing with the support from GIZ.

Significant achievements have been made for increasing the geographical coverage of TVET provision throughout the country. During the reporting period, Georgian citizens of the following regions were able to access to vocational education:  Mtskheta-Mtianeti (Kazbegi and Tianeti municipalities), Kakheti  (Lagodekhi municipality) and Samegrelo (Khobi municipality). Ministry continued progression with the public-private partnership model and ensured the agreement with construction company “M2” to jointly establish construction college in Imereti region, Zestaponi municipality. College „Construct 2” was opened in November, 2018. Adding new location lead to new more than 1000 free student places.  Construction work is also ongoing  in the Municipalities of Kaspi (Shida Kartli), Khulo (Adjaria) and Chokhatauri (Guria) with the plan to finalize the renovation in 2019.

With the support from donor organizations, Ministry ensured the development of new brand and communication strategy for increasing the awareness and attractiveness of TVET field. It is planned to start implementation of the strategy from 2019.

Professional orientation component has been strengthened in public schools since 2017 with the special program funded by the Ministry. Material technical base of public schools has been improved and in partnership with TVET colleges the vocational skills development classes became available for the pupils of 8th and 9th grade.

TVET Funding:

It should be noted that, in 2017 the actual execution of State budget in the field of vocational education amounted 36,5 million GEL.

Budget of 2018 consists of  43,8 million GEL and execution by  December 3rd 2018, is 37,8 million GEL.

Increasing the scale of the reform led to increased state budget for TVET sector. 2019 year state budget project estimates 64mln GEL (in accordance with project of State budget of 2019), that would contribute to introduction of new law and the targets set until 2025 (increased participation rate of youngsters and adults).

## Strategy task 1: Compliance of vocational education with requirements of labour market and internationalization of the system

Georgia envisions internationalization of TVET sector as a key aspect for attractiveness and quality education. Adoption of new qualification framework that is in compliance with EU NQF, is the bases for better skills in Georgia demanded on the international labour market as well as for initiating the exchange programs. International experience shows that the mechanism for ensuring the relevance of the sector to employers’ needs is engagement of social partners in formation as well as in provision of education. Social partnership in Georgia has always been challenging that is slowly progressing with establishing different strengthening mechanisms, such as involvement of employers in policy advisory boards, sector councils and in WBL model.

Georgia labour market studies along with technical vocational skills name generic skills as the demanded for employment. This was the reason for putting the general skills development modules as obligatory parts of each new programs, such as: communication, literacy, numeracy, foreign language, entrepreneurship etc. Innovative learning methods have been piloted in majority of the TVET schools using the modern facilities arranged in all public providers.

Activity 1. Participation of social partners and civil society in the process of developing the vocational education

Participation of social partners and civil society is ensured at all levels of development of vocational education: macro, mezzo and micro. National VET Council, Sector Boards, Supervisory Councils of Vocational Educational Institutions engage employers.

National VET Council represents the main advisory body to the Minister, established since 2015 as quadripartite body. Employers Association, trade union and civil society together with the government work on the policy making level. During the reporting period the following important policy documents have been discussed by the council: draft new law on vocational education; draft of unified strategy on education and science (2017-2021), the rule of recognition of non-formal education, new version of authorization standards. 4 thematic working groups have been working under the council in 2017-2018 (Work-based learning, Teachers’ professional development,  Inclusive education and Quality enhancement) Social partners actively participated in the working groups.

In 2017-2018, 11 Sectorial Councils have been functioning under the LEPL National Centre for Educational Quality Enhancement, which were also formed on the principle of social partnership. The functions of the Sectorial Councils include: supporting the process of ensuring compliance between vocational education standards and labour market needs; validation of vocational education framework programs; Various capacity building activities have been provided to the council members in order to strengthen their engagement level and technical expertise.

Supervisory boards represent the integral part of TVET providers’ management scheme. It is obligatory to form the board with local government, social partners and civil society representatives and agree basic decisions with them.

Activity 2. Development and implementation of mechanisms for comparability, recognition and mobility of Georgian professional qualifications with European system:

The main instrument for comparability of Georgian professional qualifications with European system, is national Qualification Framework. It is the basic instrument for promotion of skills mobility and establishment of continuous educational system for the students and the employees. NQF referencing to EQF ensures that qualifications are easily perceptive and understandable for the various countries and systems in European space. It also gives opportunity to compare the country’s national qualifications with other country’s qualifications. Georgia has approved the NQF on 10th of December, 2010. It represents the combination of three basic sub-systems (general, vocational and higher education) and links qualifications on different stages and types, hierarchically from the lowest to –the highest level.

However, in 2014 Georgian National Qualification Framework was analysed with respect to EQF and the specific dimensions have been revealed (description of learning outcomes, the progression of qualifications- horizontal and vertical etc.). On bases of the analyses, NEW draft NQF was prepared and the discussions with the interested parties/organizations have started. By the legislative amendments made in 2018 (including a new law “On Vocational Education”) the legal basis for approval, implementation and further development of NQF is already in place.  Herewith, for the purpose of support the NQF implementation, together with the “European Funding Education (ETF), new EU support „Twinning Project“ is accessible for Georgia. Launching of the project is planned for January, 2019 and will last for 2 years.

New NQF as well as new law enables the system to start the recognition of informal-non formal education, formalization of training and retraining programs etc. New Law on Vocational Education envisions the opportunity to formalize exchange and joint programs. However, international partnership has enabled the college students and graduates to participate in international programs with Estonia, Poland and Germany.

- Within the framework of the Georgian-Estonian project “Share of the best Estonian experience, for supporting the compatibility in the sector of Georgian vocational education”, in the first half of 2018, the students of LEPL Community College “New Wave” were sent to Estonia under the Cooker’s program for 2 weeks internship, as well as the Estonian students visited Georgia too. Moreover, in the second half of 2018, 4 vocational students of the logistic program of the same college travelled to Estonia for 2-year study.

- 40 students of Non-Entrepreneurial (Non-Commercial) Legal Entity College “Ikarosi” were sent to Germany on 3-month internship. Students passed internship in 24 hotels. The College co-operates with these hotels on bases of Memorandum. The students and graduates of Ikarosi also took an active participation in different types of master classes and competitions in Slovakia and Poland. It should be noted that in the third quarter of 2018, 12 vocational students and 6 administrative representatives from Slovakia also visited College “Ikarosi”.

- In 2017 the Georgian team participated in the 44th International Competition of Worldskills International, which was held in the United Arab Emirates. Georgian team was represented in seven professions: cuisine, confectionery, restaurant service, hairdressing, graphical design, information technology and website design.

Activity 3: Development of the vocational programs in line with labour market needs:

Vocational education program reform started in 2014. Initiative focused to modularization of the TVET programs leading the competence based teaching.    Modular programs focus not only on the development of technical skills, but also on the development of basic, generic skills as well as key (Entrepreneurship, communication in foreign language, digital competences, etc.) skills. Correspondence with the requirement of the labour market, orientation on learning outcomes, strengthening the practical components and modern approaches of teaching and student assessment, are basic characteristics of modular programs. Methodology of modular program development was recommended by EU TA. In the process of formations of vocational qualifications, employers, representatives of Sector Associations/Unions are actively involved. The process of development of the standard and framework program includes the following: identification of relevant teaching sphere and descriptor  (ISCED) in the international classifier of education, identification of the vocation in the international classifier (ISCO), types of economic activities in Georgian national classifier-identification of the positions relevant to the field, sharing  the international experience, which means studying the information (two EU member countries among them) about the level of qualification, assumed content of framework document/module and structure on the example of minimum 3 countries. Namely, by passing those stages, up to 200 professional standards have been renewed and up to 110 modular programs have been approved and introduced. Currently 70% of the programs are modularized and from 2019 the system would fully be compiled by new programs.

With the support from the Millennium Challenge Fund-Georgia (MCA-Georgia) significant investment was made in TVET sector with particular focus on development of new qualifications and associated facilities in the education institutions. Obligatory partnership of provider and private sector was the requirement for grant component and as a result more than 40 new high quality programs in STEM, tourism and agriculture field were developed in accordance to international standards and with participation of employers.

All new standards and framework programs are available for public on the web page www.vet.ge that serves as a registry for new modules.

Activity 4. Development and introduction of the quality assurance system:

As it has been stated, one of the main goals of the reform in improvement of education quality. Current methodology of quality assurance includes institutional as well as program authorization (adding the program); Monitoring is one of the applicable tools for the NCEQE as well.

With the support of EU and MCA TA projects new framework of quality assurance has been drafted, initiating the verification system as a new mechanism. New guideline including new internal and external quality assurance scheme is also available helping the piloting process.

Important changes have been made in improving the authorization standards. Attention was paid to the following aspects: institutional development of the providers and assistance in the development of their resources, context of modular programs, stimulation of development of internal mechanisms of quality assurance etc. Consequently, the number of standards have been increased from 3 to 5 adding the following criteria: mission and the strategic development of the college, supportive measures to vocational students. In accordance with the amendments to law on Educational Quality, the renewed mechanisms of quality assurance will be introduced in 2019.

Constant support to increase the quality of education is available from NCEQE to education institutions through series of the trainings and orientation meetings concerning to introduction of modular teaching as well as the internal quality enhancement mechanisms.

In 2017-2018 NCEQE activated the process of monitoring of private and public colleges and paid 31 planned and 18 non-scheduled monitoring visits in the educational institutions.

Activity 5: Support of continuous professional development of vocational education teacher and attraction of new personnel:

TVET teachers professional development is anticipated as the core mechanism for increasing the teaching quality.  TPDC (teachers’ professional development centre) together with the Ministry and donor society (EU, UNDP, GIZ) is continuously working on creation of transparent system for teachers’ induction, development and career advancement; the work is ongoing on the regulation of the profession with the goal to attract more young practitioners.  Since new law on VET enables to start development of new model, it is planned from GGF to support the Ministry with finalizing the regulatory framework and formalize in 2019.

Meanwhile the capacity building of teachers according to system needs is ensured. TPDC is in charge of provision of trainings in pedagogics, modular teaching, inclusive vocational education, entrepreneurial learning, student assessment and training in enterprises. Exchange programs for teachers with the help of international organization is insured (“Informational Centre of NATO and EU”-10 teachers in Slovakia) .

With the support from EU TA, 50 teachers were trained on international mobility.

Besides the abovementioned, with the support from the German Government through the organization "Senior Expert Service (SES)" experts visited Georgia for on the job training. They supported the teachers of tourism and construction field.

Activity 6. Strengthening entrepreneurial education and work-based learning for employment and self-employment of graduates

Entrepreneurial module became the obligatory part of new modular programs. Although, prioritization of the entrepreneurial learning, requires more advanced approaches for reaching the goal. In 2018, Ministry is being supported by Davis University (US Embassy grant) with the project targeting to project based approach within the frameworks of the entrepreneurship module. It is planned to start proactive introduction of EU adopted EntreComp and the system would have UNDP/SDC active assistance on the topic as well.

Ministry facilitates this component with active engagement in the processes. In order to have good coordination, the working group has been formed led by the department. Descriptive research in the system about the entrepreneurial education was conducted and the action plan was based on the results.

Industrial innovative laboratories (Fub labs) are arranged in 14 TVET centers and they are used as a means of innovative learning and facilitation of entrepreneurial activities for the students. Results are promising with several successful start-ups.  “Hakatons”, “Busters” have been organized to foster the attractiveness of students towards entrepreneurship and use of modern technologies. Ministry efficiently cooperates with Innovation Center of the Ministry of Economy.

Work based learning is a new approach for Georgian TVET system. As a results of the pilots in 2016, the volume of the programs that envision the reaching of more than  50% of learning outcomes in real working environment, has been expanded. In 2017 and 2018 dual programs in tourism, railway transportation, construction and engineering have been added to agricultural sector, compiling 23 altogether. It is planned to move to IT and Transport and Logistics in 2019 with the assistance from GIZ.

Ministry also actively works on sub legal act regulating the WBL system.

Indicator of the first strategic task

- Increased employment rate of TVET graduates:

- 2016 Tracer Study result – 56% of graduates are employed.

- 2017 Tracer Study results – 56.2% of graduates are employed.

Note: Results of the study of 2018 will be available in the first half of 2019.

- Increased number of dual programs:

- 2016 year - 3 dual programs in the field of agriculture.

- 2017-2018 – more than 20 dual programs in the fields of agriculture, tourism and construction

## Strategic task 2: Ensuring the accessibility of vocational education, based on learning principal throughout the lifetime

Bases for Unified Strategy of Education and Science is LLL principle. New system of vocational education is critical in the dimension and the links of TVET to other levels of education, created and ensured within the new law are core aspects. The formal system of adult education will also strengthen the life - long learning in Georgia.

By integrating the general education with the vocational education, students who will receive the vocational education on bases of basic education, will be able to proceed learning on the stage of academic education. Moreover, it will be possible to recognize the credits on the higher education which were gained during the vocational education. In the strategy, important attention is paid to the possibility of recognition the competences achieved within the formal education and to the establishment of the recognition system of informal education, which shall stipulate improvement of the components and learning throughout the lifetime. It should be noted that for the purpose of improving the accessibility on vocational education it is important to establish optimal network of educational institutions.

Activity 1: Links of vocational education with other levels of education and elimination of education deadlocks:

New law on vocational education has created firm legal basis for realization of lifelong learning principle. The law aims at improvement of the quality and flexibility of the vocational education provision, including accumulation of the credits and establishment of the transferring mechanisms. Law foresees formalizing the adult education and creates basis of delivery the general education within the vocational frameworks.

Before the enforcement of the law, preparatory work for integrating the general educational into VET started successfully assisted by UNDP/SDC project. In 2017, two program pilots started on the IV level.   Monitoring revealed interesting findings and recommendations for systematization of the methodology.  From May, 2019 TVET providers will start offering new type of programs with the plan to complete the integration in 2 year on.

New education program will be offered in the form of associated degree so called short cycle. The concept envisions improvement of practicality of academics programs, recognizing the credits on Bachelor programs and engaging the Universities in offering the TVET courses. Preparation work has started with the assistance from Good Governance Fund.

As it was already emphasized, new Georgian law on vocational education opens the way to the different targeted groups to get opportunities in life long perspective. By developing adult education system  it will be possible for any citizens of Georgia, including those who were left without getting the basic education, to be enrolled in short courses and get certification or get the opportunity to recognize non formal and informal education;

Activity 2. Flexibility and inclusiveness of the system:

One of the priorities of the reform of TVET sector is to ensure universal accessibility.  Correspondingly, the needs of various vulnerable groups, persons with disabilities, with special education needs, national minorities, IDPs and socially unprotected population is crucial while developing the educational services. Public TVET institutions provide special services to the above-mentioned groups (Sign-language translators, supportive staff, specialists of inclusive education), adapted learning materials are developed, special trainings for teachers are constantly planned and provided.

In 2017-2018 the number of the students with special education needs who were enrolled in vocational program increased up to 500. From 2016, public TVET institutions offered programs to ethnic minorities based on the unified tests in Azerbaijanian, Armenian and Russian languages, after which they pass the module Georgian language and move to studying the profession.

In order to support IDPs, Agency of livelihood Sources in partnership with the Ministry, developed the project aiming at funding the transportation expenses for those IDPs entering the TVET. Agency also supports IDPs entrepreneurial activity, the grant competition was announced and as a result, up to 100 projects were financed in 2017-2018.

In 2017-2018 implementation of short-termed vocational courses suitable for different targeted groups were actively ongoing, in which job seekers, convicts and former prisoners were involved:

- In 2017, the preparation –retraining program was passed by 1135 convicted and former prisoners; in 2018 up to 1000 beneficiaries were covered (final data will be available in the beginning of 2019).

Also within the framework of the State program of vocational training - retraining and raising of qualification of job seekers by the vocational educational institutions:

- In 2017, 2130 beneficiaries passed the training; in 2018,  first stage  - 2064 persons are engaged (the data of the second stage of 2018 will be available in the beginning of 2019).

Availability of dormitories at TVET providers’ is a very important for enabling the citizens to get their interested profession if the TVET centre is not accessible in their municipalities, Thus, in 2018, Ministry finalised the construction and equipment of the dormitory in Kutaisi College for 80 students. The work has started in Mestia, Senaki and Tsalenjikha municipalities.

Accessibility to upgrading the skills for adults has not been ensured in formal education system in Georgia. The qualification programs with the duration of 2 years are not flexible for the adults wanting the get skills upgrade. Significant step forward was the legislative bases, new NQF and new institutional set-up in the department for TVET. Special division has been formed to take care about the topic, that will proactively be enforced from January 2019.  Ministry envisions the full participation of private sector and private training centres in delivery of short term courses, that would lead to better quality and employability of those willing to step in. Formal certificates would help the beneficiaries to get better wages or apply to qualification programs and recognize some credits.

Activity 3. Development of effective mechanisms of recognition of the formal and non formal education:

Elaboration of the rule of recognition and transfer of credits is ongoing with the plan to formalize in the 2nd quarter of 2019. Document aims at recognizing achieved learning results in formal education programs.

For the recognition of non formal education, special methodology was developed base on the best international practice; piloting of the methodology was arranged in three programs and based on its results the common approach was elaborated that will be adopted in the first quarter of 2019.

Activity 4. Creation of diversified funding mechanisms:

Diversified funding mechanisms means the existence of various sources and opportunities of funding the vocational education. New system development naturally requires new model of funding to be adopted by the government.  Specific model shall be approved by the State after a comprehensive analysis of the current practice of funding and a new concept will be developed involving analyses of best international practice.  Important innovation is that law enables the government to fund the private providers according to state priorities. However, It should be noted that, the private providers were funded by the government for certain program and service delivery. For ex.: private educational institutions actively participated in the job seekers retraining state programs; They are also involved in school programs for vocational skills development.

It is noteworthy, that due to the new law, Legal entity of public law-vocational education institution is authorized to attract the additional funds permitted under the Georgian legislation, including, getting of the income from economic activities, which is not dangerous for the human health and does not influence negatively on the learning quality. Generated funds shall be spent only for the implementation of the institutions goals and for the execution of their functions. It is important to note that government resolution will give the clear instruction about the product realization principles avoiding some dumping of private sector nearby.

Activity 5:  Development of unified, accessible, flexible network of vocational institutions (State and Private)

Significant progress was achieved in 2017-2018 in terms of increasing the geographical accessibility to VET. Establishment of new colleges and development of new branches has been the priority for the Ministry including the PPP approach.

In 2017-2018, students were enrolled for the first time in Kazbegi and Tianeti (Mtskheta-Mtianeti),also Lagodekhi (Kakheti) and Khobi (Samegrelo) Municipalities. Construction is ongoing in Kaspi (Shida Kartli) and Khulo (Adjaria) municipalities. Financial resources have been given to College “Horizonti” for opening brand in Chokhatauri (Guria) municipality.

As it has been announced Ministry introduced new PPP concept and DBOM model was used for expansion of the network. Agreement concluded between the Ministry of Education and JSC “M2 Real Estate” in the Municipality of Zestaponi led to the establishment of construction college „Construct 2”, that was opened in November. The college will receive nearly 600 applicants from 2019.

In 2017, Kobuleti college in partnership with private construction company, opened branch in Batumi. Tourism field programs are offered in newly equipped centre mainly focusing on short term courses.

Annual rehabilitation plan included the renovation of the college buildings in several locations. Full rehabilitation  was financed for College “Prestige”, College “Modusi College “Iberia” and the partial rehabilitating works were ensured to 5 educational institution.

Construction of the students dormitory was finished in Kutaisi; Construction of dorm is planned in colleges of Mestia, Tsalenjikha and Senaki.

On bases of the minimal technical equipment standards of the modular programs, the colleges upgraded equipment and workshop facilities, necessary for the implementation of the modular programs.

Diversification of vocational education providers network is one of the main focus of the reform. It is foreseen to involve the private sector (companies) training-centres in the process of delivery formal education, in particular delivery of the retraining programs. Concept on Adult education system development including the models was prepared in the last quarter of 2018 and the actual implementation of the initiative will start from the next year to achieve the targets set for the participation. It will also be possible to involve the suppliers of the non formal education nowadays existing in the system in the delivery of the formal training.

Indicator of the second strategic task

- Increased number of student moving to next level of education

- 2016 Tracer Study - 6 % of the graduates of the vocational programs continue studies in the higher educational institutions.

- 2017 Tracer Study- 8 % of the graduates of the vocational programs continue studies in the higher educational institutions.

- Data of 2018 will be available in the first half of 2019.

- Increased participation of adults in the educational programs.

According to the study made by the Georgian Statistics Office (Goestat) in 2016 the rate of the adults participation in the educational programs was 0.42%. As for 2017, it was 1.6%.  The difference between those two data is caused by changing the study methodology. The data of 2018 will be available in the first half of 2019.

## Strategic task 3: Promotion of vocational education and increasing its attractiveness

According to the strategy, the improvement of the image of vocational education represents a strategic task. For promotion and attractiveness, several basic directions are emphasized: spreading the information about the successful employment of the vocational student, arrangement of the PR campaigns about rising the awareness, improvement of the professional orientation system, system flexibility, creation of a new brand of vocational education and implementation of communication strategy based on active marketing campaign.

Activity 1. Development of the professional orientation and career planning service:

Professional orientation and career planning service provision, in a way, is a joint effort of cooperation with the Occupied Territories, Labour, Health and Social Affairs of Georgia. According to joint vision, standards and methodologies have been developed with the help of EU TA. Capacity building activities for the specialists have been provided during the reporting period.

Moreover, by the new law on vocational education under the obligation of the Ministry of Education, Science, Culture and Sport of Georgia, it is defined the development of the system of professional orientation, and career guidance in the formal education. System should provide assistance of any person willing to get the service, so that at any stage of education he/she can identify,  own opportunity, competence and interest for making decision regarding the choosing of the education and profession and can manage own career. On the current stage, at all public professional educational institutions one staff member is assigned for professional orientation and career planning. With the assistance from MCA the profile of professional orientation and career planning managers was developed with job description.

In order to develop the professional skills among school pupils, Ministry adopted special program. Since 2017, based on the particular pilots, methodology has been defined and used for ensuring the funds for public as well as for private TVET providers for partnering with schools, improving the facilities at schools and building the capacity of teachers. The program had several targets: 1. Professional orientation; 2. Attraction of more beneficiaries to VET; 3. Enhancing the schools to become TVET providers in future.  education.

As a result, 200 projects in Tbilisi and in regions were successfully implemented. . 25 colleges and 138 public schools were involved in the projects. In 2018 the number of projects have been increased. In the current year, 348 projects were implemented with the involvement of 28 colleges and 221 public schools. Totally, in 2017-2018 more than 7000 school pupils participated in the aforementioned activities.

Activity 2. Creation of the new brand of vocational education and implementation of the communication strategy:

For rising the attractiveness of the vocational education, new brand of vocational education and communication strategy were developed aiming at airing more on the opportunities of TVET sector for all groups of the society.  It is planned to start using various communication techniques from 2019 to kick off the action plan implementation.  All this efforts are considered to significantly improve effectiveness and attraction of the society to TVET. During the reporting period, for strengthening the image of vocational education, various types of communication activities were planned and implemented: fairs, exhibitions, “Hakathon”, “Creaton”, innovative learning week, image clip on social media, open door days etc.

In 2017-2018 Georgia joined “European week of vocational education”. With the support from the donor organizations, several large-scaled conferences were held: MCA –“TVET annual conference” and awarding ceremony “National Award of Vocational Education”;  Also, in 2018 under the message - “Better Skills for Betted Employment” EU delegation supported the event  dedicated to sharing the results of the reform of employment and education and represented result of four year cooperation.

In 2018, Ministry of Education, Science, Culture and Sport of Georgia hosted the regional conference of the Eastern partnership, aiming at sharing the experience on work based/dual education among other partner countries. The conference was held in facilitation with European Training Foundation (ETF) and 50 delegates from 6 countries (the Ukraine, Belarus, Azerbaijan, Armenia, Moldova, Kazakhstan) participated in the conference.

The Third Strategic Task Indicator

Rising Public Awareness of Vocational Education

According to the survey (2015) of the public attitude to vocational education the attitude of society is growing positively (number of respondents – 72%). it is desirable to carry out additional research on the topic.

In scope of EU technical support the survey was carried out in the following cities/towns: Tbilisi, Kutaisi, Batumi, Gori, Rustavi; 1920 respondents were interviewed (people of age 15-24 who learnt/haven’t learnt at vocational schools). Field works were done in August 2017. 20% of respondents think that the attitude to vocational education is positive, 49% thinks it is neutral, while 27% think that it is negative, 5% hesitate to answer; 40% of respondents think vocational education is trendy, 75% think that it is useful.

## Budget

Mln GEL

| Title | 2013 year act | 2014 year act | 2015 year act | 2016 year act | 2017 year act | 2018 year final |
| --- | --- | --- | --- | --- | --- | --- |
| Vocational Education | 13.3 | 23.2 | 33.0 | 33.7 | 36.5 | 43.8 |
| Including Voucher | 3.7 | 11.8 | 11.5 | 12.3 | 14.1 | 14.1 |
| programmed/targeted | 5.6 | 3.0 | 6.9 | 9.4 | 12.3 | 14.3 |
| Supporting modular educational programmes |  |  |  |  | 0.12 | 0.13 |
| Subprogram on labour skills development among pupils |  |  |  |  | 1.3 | 2.0 |
| Infrastructural development | 2.9 | 6.9 | 12.3 | 10.0 | 8.2 | 12.5 |
| VET teacher professional development program | 0.1 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 |
| LEPL - national assessment and examination center (VET student testing) | 0.5 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 |
| Promoting vocational education and civil integration for national minorities |  |  |  |  | 0.0 | 0.3 |
| Development of vocational qualification system | 0.4 | 1.2 | 1.9 | 1.5 | 0.0 | 0.0 |

## Risks and the Ways of their Mitigation

| № | Description | Reaction |
| --- | --- | --- |
| 1 | Obstacles to adopting/realizing new law/legislation act (on vocational education) | Consultations with a decision maker, permanent informing of the interested parties, lobbying the issue in respect institutions |
| 2 | Lack of financial resources caused by local economic development impediments or the lack of international financial support | Mobilization of resources in order to effectively use state finance support, involvement of private sector into vocational education sphere, finding donors |
| 3 | Priorities shifting whether on national or sector levels | Concentrating private sector, teachers’ and public attention to support the strategy. Informing about the budget, economy and the results |
| 4 | Resistance to reforms of decision makers, especially on the administrative level of institutions | Growing the role of vocational education beneficiaries in administering and strategy development processes at educational institutions |
| 5 | Possibilities of institutions engaged into reforms and their coordination | Measures to widen possibilities in terms of the existing resources |
| 6 | The lack of interest of private sector to engage into reform process | Measures to rise public consciousness; offer for cooperation |
| 7 | Lack of awareness of the society and stereotypes | Vocational education branding, information campaign |
| 8 | Resistance to innovations and new ideas | Adopting international experience, e.g. EU’s experience in the field of vocational education, international challenges etc. |

## Conclusion and Recommendations

The report concerns the basic guidelines of 2017-2018 Action Plan and its results in the field of vocational education in the scope of Education and Science Strategy (2017-2020).

According to the strategy the priorities are:  relevance of vocational education to labor market needs, system internationalization, life-long learning based vocational education development, popularization of vocational education and rising  its attractiveness.

The new law makes a legal bases for overcoming the system challenges. The law gives opportunities to new wave of the reform in scope of which, Ministry started to develop the education system for adults and integration of general education into VET (IV level). Vocational education will be linked to the higher education  via programs of so called “Short Cycle”; credits received on the stage of vocational education will be recognized in higher education; work-based learning forms will be up scaled etc. the new law will make it possible to reach goals that were set by the strategy and Action Plan. It is important to share the best practices in the process of implementation in order to achieve good results.

Successful realization of the strategy is not merely a single department or ministry responsibility. It takes a participation of agencies, social partners, educational institutions and international organizations in the process of implementation of the vocational education reform and the new law on vocational education. It implies the development of coordination mechanisms with the Ministry of Education, Science, Culture and Sport. In the process of introduction of the new law  the possibilities of the respective  agencies and vocational education institutions should be grown together with those of the Ministry.

According to new legislation the system changes are in connection with adopting and implementation of the new national qualification framework which is in line  with European qualification framework. It is important that the national qualification framework is  adopted and realized in January 2019 according to the Plan. System internationalization work should be started especially in order to establish international and scholarship programs.

According to the new system it is important to revise the existing financial model and establish effective new, diversified model. Financing sources must be expanded, motivation of the private sector must grow, new investment should be available. Sector level must be emphasized in the aspect of social partnership that will enhance relevance between the skills and labor market. Involvement of private sector is essential in the sense of practice planning and in the process teaching-evaluation, monitoring and qualification. It is important to enhance models of public and private sector partnership in scope of work based learning and not only.

In spite of many quality assurance activities the quality of vocational education is still the challenge. It is important to continue work to enhance the quality and to introduce new internal and external mechanisms for ensuring the high quality. Qualified teachers are also very important aspect.  A new system for teachers to enter vocational education sphere is needed, so teachers will have an opportunity to develop professionally and be successful in their career. New model will help teachers to develop professional skills and will attract new staff to the field.

It is important vocational education to be available for everyone despite their social and economic condition, abiding place, nationality, gender, physical and mental capabilities and especially for vulnerable groups. To this end educational network must be  more flexible in the future: new educational institutions must be established, short and long term courses must be provided (training courses) at works, e-learning courses must be introduced etc. people who are left outside of educational system must be given an opportunity to get involved in it.

Vocational education is still less desirable alternative compared with the higher education. Interested parties do not have sufficient information on the positive novelties in the sphere. Thus, it is important to establish active and diverse communication activities in the scope of the new communication strategy. It is also important to develop professional skills among school students and professional orientation, consulting and career planning system development must be especially emphasized.

More researches should be carried out in order to make reform more effective. Besides researches among the course graduates interested parties attitude should be periodically learnt.

| ## The Action Plan (2017-2018) Fulfillment Report |  |  |  |  |
| --- | --- | --- | --- | --- |
| Specific goal: Rising the number of vocational students to support the country’s social and economic development; ensuring their competitive ability via developing professional and general skills |  |  |  |  |
| Strategic task 1: Conformity of Vocational Education with Labor Market Requirements and the System Internationalization |  |  |  |  |
| Task 1. Participation of social partners and and civil society in the process of developing VET policy |  |  |  |  |
| Activity | Result | Responsible Body | Year | Progress |
| Activity 1.1. Developing of the mechanism of participation of social partners and the civic society in the process of vocational education policy development. | Effective mechanisms of participation of social partners and the society in the process of vocational education policy development are developed. | The Ministry of Education, Science, Culture and Sports of Georgia. | 2017-2018 | Status: accomplished Social partners were involved into work of the National VET Council, Sector Boards, and Supervisory Boards of Vocational Education Institutions. National VET Council represents the main advisory body to the Minister, established since 2015 as quadripartite body. Employers Association, trade union and civil society together with the government work on the policy making level.4 thematic working groups have been working under the council in 2017-2018 (Work-based learning, Teachers’ professional development, Inclusive education and Quality enhancement) Social partners actively participated in the working groups. |
| Task 2. Development and implementation of mechanisms for comparability, recognition and mobility of Georgian professional qualifications with European system |  |  |  |  |
| Activity 2.1. Comparability of National Qualification Network with that of European | NQF and EQF conformity is assured | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement | 2017-2018 | Status: Partly accomplished Georgia has approved the NQF on 10th of December, 2010. It represents the combination of three basic sub-systems (general, professional and higher education) and links qualifications on different stages and types, hierarchically from the lowest to – the highest level. On bases of the analyses, NEW draft NQF was prepared and the discussions with the interested parties/organizations have started. By the legislative amendments made in 2018 (including a new law “On Vocational Education”) the legal basis for approval, implementation and further development of NQF is already in place. For the purpose of support the NQF implementation, together with the “European Funding Education (ETF), new EU support „Twinning Project“ is accessible for Georgia. Launching of the project is planned for January, 2019 and will last for 2 years. |
| Activity 2.2. Formation of vocational qualifications on the basis of international experience | Qualification is being formed on the basis of the internationally approved methodology | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement | 2017-2018 | Status: accomplished The ministry and NCEQE actively worked on the reform of educational programs (standards and framework programs) The process of development of the standard and framework program includes the following: identification of relevant teaching sphere and descriptor (ISCED) in the international classifier of education; identification of the vocation in the international classifier (ISCO), types of economic activities in Georgian national classifier-identification of the positions relevant to the field; sharing the international experience, which means studying the information (two EU member countries among them) about the level of qualification, assumed content of framework document/module and structure on the example of minimum 3 countries. Namely, by passing those stages, up to 200 professional standards have been renewed. |
| Activity 2.3. Development and implementation of joint and exchange programs by cooperating with foreign educational institutions | Joint and exchange programs are introduced | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Ehancement | 2017-2018 | Status: Partly accomplished New Law on Vocational Education envisions the opportunity to formalize exchange and joint programs. However, international partnership has enabled the college students and graduates to participate in international programs with Estonia, Poland and Germany. Within the framework of the Georgian-Estonian project “Share of the best Estonian experience, for supporting the compatibility in the sector of Georgian vocational education”, in the first half of 2018, the students of LEPL Community College “New Wave” were sent to Estonia under the Cooker’s program for 2 weeks internship, as well as the Estonian students visited Georgia too. Moreover, in the second half of 2018, 4 VET students of the logistic program of the same college travelled to Estonia for 2-year study. 40 students of Non-Entrepreneurial (Non-Commercial) Legal Entity College “Ikarosi” were sent to Germany on 3 month internship. Students passed internship in 24 hotels. The College co-operates with these hotels on bases of Memorandum. The students and graduates of Ikarosi also took an active participation in different types of master classes and competitions in Slovakia and Poland. In the third quarter of 2018, 12 vocational students and 6 administrative representatives from Slovakia also visited College “Ikarosi”. |
| Task 3: Development of the vocational programs in line with labour market needs: |  |  |  |  |
| Activity 3.1. Formation of vocational qualifications on the basis of professional standards developed in cooperation with employers | Professional qualifications are developed according to employers’ requirements | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement | 2017-2018 | Status: accomplished In 2018, with participation of employers, up to 200 professional standards have been renewed and up to 110 modular programs have been approved and introduced. Currently 70% of the programs are modularized and from 2019 the system would fully be compiled by new programs. With the support from the MCA-Georgia more than 40 new high quality programs in STEM, tourism and agriculture field were developed in accordance to international standards and with participation of employers. |
| Activity 3.2. Involvement of employers into development, implementation and qualification processes of vocational education programs | Employers are involved into development, implementation and qualification processes of vocational education programs | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement Educational institutions | 2017-2018 | Status: accomplished As a results of the WBL pilots in 2016, (more than 50% of learning outcomes are reached in real working environment) the number of such programs has been expanded. In 2017 and 2018 dual programs in tourism, railway transportation, construction and engineering have been added to agricultural sector, compiling 23 altogether. |
| Activity 3.3. Development of electronic system/register of vocational qualifications and their availability | Electronic system/register of vocational qualifications is available now | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement | 2017-2018 | Status: Partly accomplished The vocational qualifications and frame documents classifying process finished in 2018. All new standards and framework programs are available for public on the web page www.vet.ge that serves as a registry for new modules. The rule of development and administering the electronic register will be issued by the minister’s order which is planned in 2019. The project of the technical task necessary to create the electronic register of qualifications will be developed in the scope of new EU project “Twinning Fiche” (the project will start in January 2019). |
| Task 4: Development and introduction of the quality assurance system: |  |  |  |  |
| Activity 4.1. Renewal of quality assurance mechanisms and introduction of a new, result targeted evaluation (standards and procedures of institutional and program evaluations; monitoring; self-evaluation) | New mechanisms of quality assurance have been introduced | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement | 2017-2018 | Status: Partly accomplished Significant work has been carried out in the direction of quality assurance of TVET sector. NCEQE intensively worked together with international organizations for preparation of new internal and external quality assurance framework. Significant contribution was made by EU and MCA TA projects. Piloting of internal and external verification approaches started in 2018 year and is planned to continue in 2019 with the aim to adopt new authorization standards by the end of 2019. Important changes have been made in improving the authorization standards. Attention was paid to the following aspects: institutional development of the providers and assistance in the development of their resources, context of modular programs, stimulation of development of internal mechanisms of quality assurance etc. Consequently, the number of standards have been increased from 3 to 5 adding the following criteria: mission and the strategic development of the college, supportive measures to vocational students. In accordance with the amendments to law on Educational Quality, the renewed mechanisms of quality assurance will be introduced in 2019. In 2017-2018 NCEQE activated the process of monitoring of private and public colleges and conducted 31 planned and 18 non-scheduled monitoring visits in the educational institutions. |
| Activity 4.2. Development of institutional opportunities on the basis of the new quality assurance system | The parties involved into quality assurance process participate in opportunity development | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement | 2017-2018 | Status: Partly accomplished A quality assurance guideline was prepared which concerns all the issues of inner and external quality assurance. Experts were selected, trained and got involved into verification piloting. Detailed recommendations were prepared on the standards of authorization of educational institutions. The authorization guideline was developed. 5 meetings/seminars on quality assurance were held (total: 20 days a year). 375 people participated in different trainings and meetings. In support of module programs introduction a cycle of seminars was held on the topic of introducing authorization standards and module programs at educational institutions in 2017-2018. The seminars were attended by those who are responsible for the program development and quality assurance. The seminars covered 105 educational institutions and their 380 representatives participated. |
| Task 5: Support of continuous professional development of vocational education teacher and attraction of new personnel: |  |  |  |  |
| Activity 5.1 Introduction of a new model of Vocational Education Teachers Trainings, Entering the Profession and Continuous Development | A new model of vocational education teachers trainings, entering the profession and continuous development is introduced | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Teacher Professional Development | 2017-2018 | Status: Partly accomplished In order to create a transparent system for teachers’ induction, development and career advancement legal documents are being worked on (rules and conditions of professional development and career advancement, VET teacher ethic code, VET teacher’s professional standard). The system will be adopted in spring of 2019. The capacity building of teachers according to system needs is ensured. TPDC is in charge of provision of trainings in pedagogics, modular teaching, inclusive vocational education, entrepreneurial learning, student assessment and training in enterprises |
| Activity 5.2. Partnership with foreign educational institutions, educational visits, sharing the best international practices | Teachers share the best international practice | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Teacher Professional Development | 2017-2018 | Status: accomplished For the purpose of development of professional abilities of vocational teachers and sharing international experience and with the support of LEPL Information Center on NATO and EU 10 vocational teachers visited Slovakia. The teachers got acquainted with novelties in the fields of services, production, logistics, agriculture, and construction. They met their Slovak colleagues and shared teaching methods. With the support from EU TA, 50 teachers were trained on international mobility. with the support from the German Government through the organization "Senior Expert Service (SES)" experts visited Georgia for on the job training. They supported the teachers of tourism and construction field. |
| Task 6. Strengthening entrepreneurial education and work-based learning for employment and self-employment of graduates |  |  |  |  |
| Activity 6.1. Work-based/dual teaching programs promotion | Work-based/dual teaching programs are being implemented | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement Educational Institutions | 2017-2018 | Status: accomplished 23 dual programs in agriculture, tourism, railway transport, construction and engineering fields have been introduced. Also, by 2019 dual programs in information technologies and logistic will be introduced. Regulations of WBL were developed in 2018. The first version of the regulations is already developed. |
| Activity 6.2. Promotion of entrepreneurship education and innovation teaching (innovative laboratories, simulation teaching etc.) | Innovative teaching methods have been introduced; entrepreneurship education has been promoted | The Ministry of Education, Science, Culture and Sports of Georgia; Educational institutions | 2017-2018 | Status: accomplished Module systems that have been introduced in the system since 2014 include entrepreneurship module as an obligatory one. It requires more efficient teaching methods. In 2018, with the cooperation with Davis University, by grant support from U.S. Embassy a project was launched which aimed piloting a project-based teaching at entrepreneurship module. The entrepreneurship module will be revised in the scope of the project, its conformance with EntreComp frame will be checked and teaching resources will be prepared. In 2017, for the purpose of introducing continuous entrepreneurship teaching in the education system a work group was created at the ministry. A research and draft action plan of entrepreneurial education was developed. At 14 state vocational education institutions production innovative laboratories work to support students’ entrepreneurship ideas. In some of the institutions students and course graduates created Startups. Also, with the cooperation with Innovation and Technology Agency vocational education “hakathon” and “Booster” was done and also a weak of innovative teaching in vocational studies. Topics of innovative teaching and FabLab possibilities were discussed. Since April, 2017, in the scope of MCA-Georgia grant program flipped classroom method was introduced at “Black Sea” and “Erkvani” colleges. Flipped classroom is an interactive teaching strategy, which uses interactive methods. |
| Strategic task 2: Ensure access to vocational education based on the principle of lifelong learning |  |  |  |  |
| Task 1: Links of vocational education with other levels of education and elimination of education deadlocks |  |  |  |  |
| Activity 1.1. Integration of general education component in Vocational Education on the Basis of the New Legislation | General education components are introduced into vocational education | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement Educational Institutions | 2017-2018 | Status: Partly accomplished In 2018 a new law on vocational education was adopted. The law gives base to integrate general education elements into vocational education. preparatory work for integrating the general educational into VET started successfully assisted by UNDP/SDC project. In 2017, two program pilots started on the IV level. Monitoring revealed interesting findings and recommendations for systematization of the methodology. From May, 2019 TVET providers will start offering new type of programs with the plan to complete the integration in 2 year on. |
| Activity 1.2 Recognition of vocational education credits on the first level of academic education on the basis of the new legislation | Recognition of vocational education credits on the first level of academic education | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement Educational Institutions | 2017-2018 | Status: Partly accomplished New education program will be offered in the form of associated degree so called short cycle. The concept envisions improvement of practicality of academics programs, recognizing the credits on Bachelor programs and engaging the Universities in offering the TVET courses. Preparation work has started with the assistance from Good Governance Fund. |
| Activity 1.3 Development of mechanism for involvement into vocational education of those who left behind the education system | Mechanisms for involvement into vocational education of those who left behind the education system are created | The Ministry of Education, Science, Culture and Sports of Georgia; LEPL National Center for Education Quality Enhancement | 2017-2018 | Status: Partly accomplished New Georgian law on vocational education opens the way to the different targeted groups to get opportunities in life long perspective. By developing adult education system it will be possible for any citizens of Georgia, including those who were left without getting the basic education, to be enrolled in short courses and get certification or get the opportunity to recognize non formal and informal education |

| Task 2. Creating flexible teaching programs, models and services that are adapted to the needs of different target groups, including adults; |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity 2.1 Development/implementation of a model of teaching adults within vocational education | Model of teaching adults within vocational education is created | Ministry of Education, Science, Culture And Sport of Georgia; | 2017-2018 | Status: Partly accomplished From 2018 working on the development of the education of adults within vocational education started which means formalizing programs of vocational training and retraining. In the VET department adult education division was established. According to the prepared vision, for delivering services of training and retraining not only the requisites of educational institutions will be used but the experience of the sector of non-nformal education as well. Special attention will be paid on training-centres of private companies that are proposed by a new law on vocational education to formalize programs of vocational training and retraining (which should be voluntary) and issuing certificates acknowledged by the state based on it. |
| Activity 2.2 Implementation of educational programs focused on the needs of different target groups (Persons with disabilities/special educational needs, internally displaced persons, socially vulnerable persons etc.) and development/implementation of additional services; access to educational resources, special education teachers and dormitories | Vocational education is accessible to every target group | Ministry of Education, Science, Culture And Sport of Georgia; Educational institutions | 2017-2018 | Status: Partly accomplished One of the priorities of the reform of vocational education is ensuring universal access to vocational education. Therefore, within the reform of vocational education the needs of different vulnerable groups, such as persons with disabilities and special educational needs, national minorities, internally displaced persons, socially vulnerable persons is taken into account. For this purpose various services (sign language translators, assistant workers, specialists of inclusive education) were introduced in public vocational education institutions, adapted teaching materials were developed, special trainings for teachers were planned and conducted. The number of students with special educational needs accepted on vocational programs in 2017-2018 reached 500. Audio versions of 26 books were created in order to support the teaching process of the students with blindness, weak eyesight, dyslexia and other disorders accepted on vocational programs; From 2016, members of ethnic minorities are can apply to the public educational institutions on the absis of Azerbaijani, Armenian and Russian language tests, afterthat they pass the Georgian language module and continue studying on vocational education programs. In 2017-2018 up to 60 persons were accepted to public vocational educational institutionson the basis of non-Georgian language tests (this number doesn’t include people accepted on the autumn of 2018). In order to support the access to vocational educational for internally displaced persons, Livelihood Agency LEPL with the partnership of the ministry covered the costs of transportation of internally displaced students on vocational education. Also, to support business activities of internally displaced personsa grant contest was announced and after reviewing applications up to 100 projects were financed in 2017-2018. In 2017-2018 short-term vocational courses focused on the needs of different target groups were actively conducted and jobseekers, convicted persons and former prisoners participated: In 2017 1135 condemned and former prisoners underwent a program of train-retraining; In 2018 up to 1000 beneficiaries participated (final data will be available by the beginning of 2019). In 2017 up to 2130 beneficiariesunderwent a program of training (retraining); During the first stage of 2018 up to 2064 beneficiariesparticipated(data for the second stage of 2018 will be available by the beginning of 2019). In 2018 building the dormitory of public college Iberia LEPL was finished and was then equipped. The dormitory can support 80 students. Working on settling dormitories in Mestia, Senaki and Tsalenjikha municipalities have started. |
| Task 3. Development of effective mechanisms of recognition of the formal and non formal education |  |  |  |  |
| Activity 3.1 Possibilities of the recognition of knowledge gained in formal education for the purposes of other programs based on the renewed legislation | Based on the formulated rule knowledge gained in formal education for the purposes of other programs is acknowledged. | Ministry of Education, Science, Culture And Sport of Georgia; National Center For Educational Quality EnhancementLEPL Educational institutions | 2017-2018 | Status: Partly accomplished The purpose of the new law on vocational education is to improve flexibility of vocational education system, including establishing a mechanism for accumulating and transferring credits. Preparing a project for the rule of aknowledgement of expertise gained in formal education is planned by the end of March 2019 within which it will be possible to make learning outcomes of one educational program compatible with another. |
| Activity: 3.2 Implementing a methodology, service and monitoring of recognition of non-formal education based on the renewed legislation | System for the of recognition of non-formal education is created | Ministry of Education, Science, Culture And Sport of Georgia; National Center For Educational Quality Enhancement LEPL; Educational institutions | 2017-2018 | Status: Partly accomplished For the recognition of non formal education, special methodology was developed base on the best international practice; piloting of the methodology was arranged in three programs and based on its results the common approach was elaborated that will be adopted in the first quarter of 2019. |
| Task 4. Creating mechanisms of diversified funding |  |  |  |  |
| Activity 4.1 Development and implementation of a flexible funding model focused on the results | A new model of funding is implemented | Ministry of Education, Science, Culture And Sport of Georgia; | 2017-2018 | Status: Partly accomplished Important innovation is that law enables the government to fund the private providers according to state priorities. However, It should be noted that, the private providers were funded by the government for certain program and service delivery. For ex.: private educational institutions actively participated in the job seekers retraining state programs; They are also involved in school programs for vocational skills development. |
| Activity 4.2: Seeking additional sources for funding vocational education | Sources of funding vocational education are diversified | Ministry of Education, Science, Culture And Sport of Georgia; | 2017-2018 | Status: Partly accomplished due to the new law, Legal entity of public law-vocational education institution is authorized to attract the additional funds permitted under the Georgian legislation, including, getting of the income from economic activities, which is not dangerous for the human health and does not influence negatively on the learning quality. Generated funds shall be spent only for the implementation of the institutions goals and for the execution of their functions. It is important to note that government resolution will give the clear instruction about the product realization principles avoiding some dumping of private sector nearby. |
| Task 5: Creating a unified, universally accessible, flexible network of vocational educational(public and private) institutions |  |  |  |  |
| Activity 5.1 Improving geographical coverage of vocational education institutions | The number of providers of vocational education is increased | Ministry of Education, Science, Culture And Sport of Georgia; | 2017-2018 | Status: Accomplished In 2017-2018, students were enrolled for the first time in Kazbegi and Tianeti (Mtskheta-Mtianeti),also Lagodekhi (Kakheti) and Khobi (Samegrelo) Municipalities. Construction is ongoing in Kaspi (Shida Kartli) and Khulo (Adjaria) municipalities. Financial resources have been given to College “Horizonti” for opening brand in Chokhatauri (Guria) municipality. Ministry introduced new PPP concept and DBOM model was used for expansion of the network. Agreement concluded between the Ministry of Education and JSC “M2 Real Estate” in the Municipality of Zestaponi led to the establishment of construction college „Construct 2”, that was opened in November. The college will receive nearly 600 applicants from 2019. In 2017, Kobuleti college in partnership with private construction company, opened branch in Batumi. Tourism field programs are offered in newly equipped centre mainly focusing on short term courses. Annual rehabilitation plan included the renovation of the college buildings in several locations. Full rehabilitation was financed for College “Prestige”, College “Modusi College “Iberia” and the partial rehabilitating works were ensured to 5 educational institution. |
| Activity5.2 Diversifying providers of vocational education by developing stimulating mechanisms | Network of providers of diversifiedvocational education | Ministry of Education, Science, Culture And Sport of Georgia; | 2017-2018 | Status: Partly accomplished Diversifying a network of providers of vocational education is an important component to meet the needs of adults education.In particular, the new law on vocational education includes participating private sector (companies) training-centers in supplying formal education, particularly training and retraining programs. In the last quarter of 2018 a vision was formulated on how it will be possible today to include the providers of informal education in supplying formal education. In the near future the review of the noted vision will start with the interested parties. |
| Activity 5.3 Implementing effective mechanisms of management of educational institutions to ensure a teaching process that is adapted to the needs of students | Alternative mechanisms of management are implemented | Ministry of Education, Science, Culture And Sport of Georgia; Educational institutions | 2017-2018 | Status: Partly accomplished In order to improve mechanisms of management of vocational education institutions, activities involving development of the skills of managers and administrative staff of vocational education institutionswere carried out. In terms of EU TA two cycles of on-the job training was conducted in the Eastern and Western Georgiafor vocational guidance and career planning managers. Informational meeting was also arranged with college directors on the topics of vocational guidance and career planning. In terms of technical support project of EUtraining of the directorsof private and public vocational education institutions was conducted on “The management of project cycle”. Within MCA-Georgia project “Vocational education for economic development” a seminar was conducted on “Career education in vocational education system –partnership between educational institutions and business sector". Directors of vocational education institutions and vocational guidance and career planning managers attended the seminar. In terms of the aforementioned project another seminar was conducted on “Aknowledgment of informal education in the field of vocational education”.Directors of vocational education institutions that participate in the process of the aknowledgment of informal education attended the seminar. For effective functioning of fab labs in public vocational education institutions and active participation of vocational students in industrial/innovative processes fab lab manager’s staff was assigned for every fab lab and training for persons taking part in management of fab labs was conducted with the help of innovations and technology agency. |
| Strategic task 3: Popularizing and increasing attractivenessof vocational education |  |  |  |  |
| Task 1. Development of professional orientation and career planning services |  |  |  |  |
| Activity: 1.1 Establishing and implementing an unified model of professional orientation and career planning | An improved service of professional orientation and career planning is accessible | Ministry of Education, Science, Culture And Sport of Georgia; Educational institutions | 2017-2018 | Status: Partly accomplished In the course of development of the service of vocational guidance and career planning, the Ministry of Education, Science, Culture And Sport of Georgia actively collaborates with the Ministry of Internally Displaced Persons from the Occupied Territories, Labour, Health and Social Affairs of Georgia. Corresponding documents were prepared, including the standard of professional orientation and career planning and measures to strengthen the possibilities were implemented. Developing and adopting a strategy of professional orientation, consulting and career planning in formal education is planned. On the current stage every public vocational education institutionhas professional orientation specialists. With the support of MCA a profile and job description of vocational guidance and career planning managers were formulated, relevant questionnaire and methodology is prepared for a pilot study. |
| Activity 1.2 Stimulating the introduction of vocational education components in schools | Schoolchildren are participating in the activities that develop work-related skills | Ministry of Education, Science, Culture And Sport of Georgia; Educational institutions |  | Status: Accomplished Since 2017 the Ministry has been carrying out the program that develops work-related skills in schoolchildren. In 2017 in terms of partnership between vocational education institutions (private and public) and public schools 200 projects were chosen and executed based on competition in Tbilisi and regions. 25 colleges and 138 public schools participated in the projects. In 2018 the number of projects raised, in the current year 348 projects were executed with 28 colleges and 221 public schools participating. In total, in 2017-2018 more than 7000 schoolchildren took part in the aforementioned activities. |
| Task 2. Creating a new brand of vocational education and implementing communication strategy |  |  |  |  |
| Activity2.1 Conducting an informational campaign in accordance with the new communication strategy | Public awareness on vocational education is raised | Ministry of Education, Science, Culture And Sport of Georgia; | 2017-2018 | Status: Partly accomplished A new brand of vocational education and communication strategy was created.Necessary measures for implementing the strategy has already been planned and active implementation will start in 2019. To strengthen the image of vocational education, different kinds of communication activities were planned and carried out during the business period: fairs, exhibitions, “Hakathon”, “Creaton”, innovative learning week, image clip on social media, open door days etc. In 2017-2018 Georgia joined “European week of vocational education“ in terms of which different events were organized to raise public awareness. Also with the support of benefactor organizations several comprehensive conferences were organized: within the project of Millennium Challenge Account “vocational education for economic development" large-scale events were organized in 2017 and 2018 which included international conferences and ceremonial awarding of the winners in nominations of “National Prize in Vocational Education”. Also an event was hold in 2018 with the slogan “Better skills for better employment” during which the Delegation of the European Union to Georgia and the Government of Georgiapresented the results of 4 year partnership on employment and reforms of educational system. It should be noted that in 2018 the Ministry of Education, Science, Culture And Sport of Georgia hosted Eastern Partnership Regional Conference the purpose of which was sharing the experience based on work and dual education matters between partner countries. The conference was organized by European Training Foundation (ETF) and up to 50 delegates from 6 countries (Ukraine, Belarus, Azerbaijan, Armenia, Moldova, Kazakhstan) participated in it. |
| Activity 2.2 Strengthening the possibilities(on every level of the system) of different target groups in terms of usage of communication technology to popularize vocational education | Popularizing new brand of vocational education is being carried out using effective communication technology | Ministry of Education, Science, Culture And Sport of Georgia; | 2017-2018 | Status: Partly accomplished In terms of communication strategy strengthening the possibilities (on every level of the system) of different target groups in terms of usage of communication technology to popularize vocational education is taken into account. This will greatly improve the effectiveness and quality of the activities planned in terms of communication strategy. |